## HOME
SHRP2 Risk Management Template
HELP |  |  |  |  | Home
PROJECT INFORMATION
| AGENCY : | Federal Highway Administration |  |  |  | FACILITATOR : | Carlos F Figueroa
| LOCATION : | QDOT District 1 |  |  |  | PROJECT MANAGER : | Luis Millan
| PROJECT NAME : | QDOT Example |  |  |  | DATE : | 4224700%
| PROJECT DESCRIPTION : | QDOT Example R09 Guidebook |  |  |  | VERSION : | 2
RISK MANAGEMENT TEMPLATE STEPS
Enter base project information (schedule, cost, etc.).
Create list of potential risks.
Enter values for scales used to assess risk severity.
Enter severity information for each risk to assess risk impact.
View unmitigated risks ranked by mean severity value.
View impact of unmitigated risks on project performance and schedule.
View graphical ranking of unmitigated risks.
Enter mitigation strategies for risks selected to be mitigated.
View summary of mitigation strategies selected for each mitigated risk.
View mitigated risks ranked by mean severity value.
View impact of mitigated risks on project performance and schedule.
View graphical ranking of mitigated risks.
Step 01 - Project Structuring
Step 02 - Risk Identification
Step 03 - Rating Scale
Step 04 - Unmitigated Risk Assessment
Step 05 - Unmitigated Risk Register
Step 06 - Unmitigated Project Performance
Step 07 - Unmitigated Risk Ranking Plots
Step 08 - Risk Mitigation Strategies
Step 09 - Mitigation Strategies Register
Step 10 - Mitigated Risk Register
Step 11 - Mitigated Project Performance
Step 12 - Mitigated Risk Ranking Plots
Summary Report
Project Reset

## 1-Hidden (hidden)
Design-Bid-Build
Project Start Date |  | 4167400%
Target Date for Start of Operations |  | 4176400%
Schedule Value
| Months/Date | Early Start | Early Finish | Late Start | Late Finish | Float | 3
Planning | 0 | 4014800% | 4014800% | 4222100% | 4222100% | 68.1908 | 2
Scoping | 0 | 4014800% | 4014800% | 4222100% | 4222100% | 68.1908 | 42522
Design Funding Date | 4222100% | 100% | 4222100% |  | 4222100% | 0 | 6
Prelim Design/Environmental Process | 13.6 | 4222100% | 4263444% | 4222100% | 4263444% | 0 | 6
Environmental Permits | 0 | 4263444% | 4263444% | 4278644% | 4278644% | 5 | 42736
ROW/Util/RR Funding Date | 4222100% |  | 4222100% | -124073196% | 4278644% | 18.6 | 5
ROW/Util/RR | 0 | 4263444% | 4263444% | 4278644% | 4278644% | 5 | 4
Final Design | 5 | 4263444% | 4278644% | 4263444% | 4278644% | 0 | 43101
Construction Funding Date | 4222100% |  | 4222100% | -124073196% | 4278644% | 18.6 | 8
Procurement | 6 | 4278644% | 4296884% | 4278644% | 4296884% | 0 | 23
Construction | 18 | 4296884% | 4351604% | 4296884% | 4351604% | 0
Operations & Maintenance | 0 | 4351604% | 4351604% | 4351604% | 4351604%
Replacement | 0 | 4351604% | 4351604% | 4351604% | 4351604%
Design-Build
Project Start Date
Target Date for Start of Operations
Schedule Value
| Months/Date | Early Start | Early Finish | Late Start | Late Finish | Float
Planning | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | 3
Scoping | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | 2
Design Funding Date | 4014800% |  | 4014800% |  | 4014800% | 0 | 43101
Prelim Design/Environmental Process | 12 | 4014800% | 4051280% | 4014800% | 4051280% | 0 | 6
Environmental Permits | 6 | 4051280% | 4069520% | 4051280% | 4069520% | 0 | 6
ROW/Util/RR Funding Date | 4014800% |  | 4014800% |  | 4087760% | 24 | 43282
ROW/Util/RR | 12 | 4051280% | 4087760% | 4051280% | 4087760% | 0 | 300%
Construction Funding Date | 4014800% |  | 4014800% |  | 4051280% | 12 | 43831
Procurement | 6 | 4051280% | 4069520% | 4051280% | 4069520% | 0 | 8
Final Design | 6 | 4069520% | 4087760% | 4069520% | 4103008% | 5.0156 | 10
Construction | 16.0156 | 4072560% | 4121248% | 4072560% | 4121248% | 0 | 18
Operations & Maintenance | 600 | 4121248% | 5945248% | 4121248% | 5945248%
Replacement | 0 | 5945248% | 5945248% | 5945248% | 5945248%
Risk Brainstorm Help Table
Planning | PL
Scoping | SC
Design Funding | F1
Prelim Design/Environmental Process | PD
Environmental Permits | EP
ROW/Util/RR Funding | F2
ROW/Util/RR | RR
Final Design | FD
Construction Funding | F3
Procurement | PR
Construction | CR
Operations & Maintenance | OM
Replacement | RP
Risk Type List
Threat
Opportunity
Impact of Probability of Risk | Rating | 55
Definite | 4 | 1
Almost Certain | 3 | 14.5
More Likely | 2 | 28
Slightly More Likely | 1 | 41.5
No Change | 0 | 55
Slightly Less Likely | -1 | 41.25
Less Likely | -2 | 27.5
Rare | -3 | 13.75
Eliminate | -4 | 0
Strategy Select
Yes
No
Phases - Cost & Disruption
Planning
Scoping
Prelim Design/Environmental Process
Environmental Permits
ROW/Util/RR
Final Design
Procurement
Construction
Operations & Maintenance
Replacement
Phases - Duration |  | Phases - Duration
Planning |  | Planning
Scoping |  | Scoping
Design Funding |  | Design Funding
Prelim Design/Environmental Process |  | Prelim Design/Environmental Process
Environmental Permits |  | Environmental Permits
ROW/Util/RR Funding |  | ROW/Util/RR Funding
ROW/Util/RR |  | ROW/Util/RR
Final Design |  | Final Design
Construction Funding |  | Construction Funding
Procurement |  | Procurement
Construction |  | Construction
Operations & Maintenance
Input for copying charts |  | Replacement
Copy Thrt_Unmit? | TRUE
Copy Opp_Unmit? | TRUE
Copy Thrt_Mit? | TRUE
Copy Opp_Mit? | TRUE
Start Row - Risk Mitigation | 67
Sheet Names
1 - Project Structuring
2 - Risk Identification
3 - Risk Scale
4 - Unmit. Risk Assessment
5 - Unmit. Risk Register
6 - Unmit. Project Performance
7 - Unmit. Risk Ranking Plots
8 - Risk Mitigation Strategies
9 - Mit. Strategies Register
10 - Mit. Risk Register
11 - Mit. Project Performance
12 - Mit. Risk Ranking Plots
13 - Summary Report

## 1 - Project Structuring
SHRP2 Risk Management Template
| HELP |  | Step 01 - Project Structuring
ANALYSIS - Select the "Analysis" button on the left to enter values in the "Analysis" portion of this sheet
|  | Project Delivery Method | Design-Build |  | Include Operations, Maintenance, & Replacement? |  |  |  | Yes
|  | Selected Perfomance Measures | Schedule
Cost
Disruption
SCHEDULE
|  | Project Start Date |  | 4014800%
|  | Target Date for Start of Operations | (Open to Traffic Date) | 4121200%
|  | Schedule Value ($M/month) |  | 0.1
|  | Project Phase | Months/Date | Early Start | Early Finish | Late Start | Late Finish | Float (months)
|  | Planning | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0
|  | Scoping | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0
|  | Design Funding Date | 4014800% |  | 4014800% |  | 4014800% | 0
|  | Prelim Design/Environmental Process | 12 | 4014800% | 4051280% | 4014800% | 4051280% | 0
|  | Environmental Permits | 6 | 4051280% | 4069520% | 4051280% | 4069520% | 0
|  | ROW/Util/RR Funding Date | 4014800% |  | 4014800% |  | 4087760% | 24
|  | ROW/Util/RR | 12 | 4051280% | 4087760% | 4051280% | 4087760% | 0
|  | Construction Funding Date | 4014800% |  | 4014800% |  | 4051280% | 12
|  | Procurement | 6 | 4051280% | 4069520% | 4051280% | 4069520% | 0
|  | Final Design | 6 | 4069520% | 4087760% | 4069520% | 4102960% | 5
|  | Construction | 16 | 4072560% | 4121200% | 4072560% | 4121200% | 0
|  | Operations & Maintenance | 600 | 4121200% | 5945200% | 4121200% | 5945200%
|  | Replacement | 0 | 5945200% | 5945200% | 5945200% | 5945200%
SCHEDULE LAG
|  | Include Schedule Lag? | Yes
|  |  | Schedule Lag Parameters - Description | [5 empty] | Months
|  | Lag A - Time remaining from the finish of Environmental permitting to Lag B | [6 empty] | 0
|  | Lag B - Time remaining after completion of Environmental Permitting to finish of Procurement | [6 empty] | 0
|  | Lag C - Lag remaining from finish of Environmental permits to Lag D | [6 empty] | 0
|  | Lag D - Time remaining after the completion of Environmental Permitting to the completion of ROW/Utilities/RR | [6 empty] | 0
|  | Lag E - Time remaining to finish ROW/Utilities/RR after the ROW/Utilities/RR funding date | [6 empty] | 0
|  | Lag F - Time elapsed from the completion of ROW/Utilities/RR to start of Construction | [6 empty] | 6
|  | Lag G - Time elapsed after the start of Final Design to start of Construction | [6 empty] | 1
|  | Lag H - Time remaining after the finish of Final Design to finish of Construction | [6 empty] | 6
|  | Lag I - Time remaining after finish of ROW/UTL/RR to finish of Construction | [6 empty] | 10
|  | Lag J - Time remaining after finish of ROW/Utilities/RR to Lag K | [6 empty] | 6
|  | Lag K - Time remaining from finish of ROW/Utilities/RR to finish of Procurement | [6 empty] | 0
BASE COST (in Current Year and Year of Expenditure Dollars)
|  | Project Phase | Base Cost (CY $M) | Base Cost + Overhead Cost (CY $M) | Base Cost + Overhead Cost (YOE $M)
|  | Planning |  | 0 | 0 |  | Cost Inflation Rate (percent/year)
|  | Scoping |  | 0 | 0 |  | Preconstruction |  | 3
|  | Prelim Design/Environmental Process | 1.19 | 1.1912 | 1.2089 |  | ROW/Utility/RR |  | 3
|  | Environmental Permits |  | 0.0006 | 0.00062256 |  | Construction |  | 3
|  | ROW/Util/RR | 3 | 3.0012 | 3.1371
|  | Procurement |  | 0.0006 | 0.00062256
|  | Final Design |  | 0.0006 | 0.00063181 |  | Overhead Rate | (CY $ M/month)
|  | Construction | 11.85 | 11.8536 | 12.6677 |  | Preconstruction |  | 0.1
|  | Total | 16.04 | 16.0478 | 17.0156 |  | Construction |  | 0.225
, |  | OPERATION, MAINTENANCE & REPLACEMENT
|  | Facility Performance Period | 50 | years
|  | Discount Rate to convert CY $ to YOE $ (Net Discount Rate) | 5 | %
|  |  |  | Operations & Maintenance |  | Replacement
|  | Facility Asset Type | Asset Life Expectancy (yr) | Agency O&M Costs (CY $M/yr) | Disruption (Million-Hr/yr) | Agency Costs (CY $M/event) | Disruption (Million-Hr/event)
|  | Asset 1 | 50 |  | 0.028
|  | Asset 2 | 50 |  |  |  | 0.7
|  | Total YOE $M |  | 0 | 14 | 0 | 7
|  | Total CY $M |  | 0 | 5.1 | 0 | 6.6
DISRUPTION
|  | Disruption Value |  | 10 | $M/M-hr
|  | Agency/User Cost Discount Factor |  | 1
|  | Project Phase |  | Disruption
|  |  | M Veh-Hours/Day | No. of Days | M-Hrs | Cost ($M)
|  | Planning |  |  | 0 | 0
|  | Scoping |  |  | 0 | 0
|  | Prelim Design/Environmental Process |  |  | 0 | 0
|  | Environmental Permits |  |  | 0 | 0
|  | ROW/Util/RR | 0.02 | 10 | 0.2 | 2
|  | Procurement |  |  | 0 | 0
|  | Final Design |  |  | 0 | 0
|  | Construction | 0.05 | 10 | 0.5 | 5
|  | Operations & Maintenance |  |  | 1.4 | 14
|  | Replacement |  |  | 0.7 | 7
|  | Total Disruption through OMR |  |  | 2.8 | 28
SUMMARY
|  | Project Phase | Total CY Cost ($M) | Total YOE Cost ($M) | Duration (months) | Early Start | Early Finish
|  | Planning |  | 0 | 0 | 4014800% | 4014800%
|  | Scoping |  | 0 | 0 | 4014800% | 4014800%
|  | Prelim Design/Environmental Process | 1.19 | 1.2089 | 12 | 4014800% | 4051280%
|  | Environmental Permits |  | 0.00062256 | 6 | 4051280% | 4069520%
|  | ROW/Util/RR | 3 | 3.1371 | 12 | 4051280% | 4087760%
|  | Final Design |  | 0.00062256 | 6 | 4069520% | 4087760%
|  | Procurement |  | 0.00063181 | 6 | 4051280% | 4069520%
|  | Construction | 11.85 | 12.6677 | 16 | 4072560% | 4121200%
|  | Operations & Maintenance | 0 | 0 | 600 | 4121200% | 5947450%
|  | Replacement | 0 | 0 | 0
|  | Base Cost (YOE $M) | 17.0156
|  | Base Construction Completion Date | 4121200%
|  | Months to Construction Completion | 35 | (through Operations, Maintenance, & Replacement)
|  | Base Disruption ($M) | 28 | (through Operations, Maintenance, & Replacement)
FWD===>
HOME
Clear All
Analysis
Schedule
Lag
Cost
OMR
Disruption
Create Project

## 2 - Risk Identification
SHRP2 Risk Management Template
HELP |  | Step 02 - Risk Identification
| Risk Label | Description of Risk Table Below Fills by Selecting "Create List of Risks" Button Above | Project Phase | Retire Risk?
| PL-2 | Opposition to removing access to US-555 fro 12th St. | Planning | No
| PL-3 | Opposition to "splitting" alignment of SH-111 in the interchange area. | Planning | No
| PL-4 | Other stakeholder issues not captured separately. | Planning | No
| PL-5 | Project funding delayed or reduced. | Planning | No
| SC-1 | Change in East-West project limits. | Scoping | No
| SC-2 | Change in North-South project limits. | Scoping | No
| SC-3 | Additional local improvements required. | Scoping | No
| SC-4 | Increased aestethetics for US-555/SH-111 interchange. | Scoping | No
| SC-5 | Replace culvert over Wandering Creek. | Scoping | No
| SC-6 | Provide new lighting throughout project. | Scoping | No
| SC-7 | ITS added to this project. | Scoping | No
| PD-1 | Shift alignment of US 555 at east end of project | Prelim Design/Environmental Process | No
| PD-2 | Split alignment of SH-111 at US-555 interchange. | Prelim Design/Environmental Process | No
| PD-3 | Change in configuration of SH 111 / US 555 interchange. | Prelim Design/Environmental Process | No
| PD-4 | Ground improvement required in interchange area. | Prelim Design/Environmental Process | No
| PD-5 | Shoulders required on US-555. | Prelim Design/Environmental Process | No
| PD-6 | Shoulders required on SH-111. | Prelim Design/Environmental Process | No
| PD-7 | Additional cost for signalized intersections. | Prelim Design/Environmental Process | No
| PD-8 | Change in pavement section and/or type. | Prelim Design/Environmental Process | No
| PD-9 | Rehabilitate instead of reconstruct existing roadway (e.g., overlay instead). | Prelim Design/Environmental Process | No
| PD-10 | Change in stormwater design standards. | Prelim Design/Environmental Process | No
| PD-11 | Cannot use City sewer system for project runoff (or City charges for use). | Prelim Design/Environmental Process | No
| PD-12 | Structures impacted by Main Street realignment are eligible for Historic Register. | Prelim Design/Environmental Process | No
| PD-13 | Change in environmental documentation. | Prelim Design/Environmental Process | No
| PD-14 | Delays completing environmental documentation. | Prelim Design/Environmental Process | No
| PD-15 | Encounter unanticipated contamination in interchange area. | Prelim Design/Environmental Process | No
| PD-16 | Additional wetland mitigation required for planned alignment. | Prelim Design/Environmental Process | No
| EP-1 | Challenge to environmental determination or permits | Environmental Permits | No
| EP-2 | Delay obtaining the 404 permit | Environmental Permits | No
| RR-1 | Uncertainty in ROW inflation rate | ROW/Util/RR | No
| RR-2 | Accelerating pace of development in interchange area | ROW/Util/RR | No
| RR-3 | Unwilling sellers | ROW/Util/RR | No
| RR-4 | Additional relocation or demolition required | ROW/Util/RR | No
| RR-5 | Additional ROW required for planned project | ROW/Util/RR | No
| RR-6 | Other delays to ROW planning | ROW/Util/RR | No
| RR-7 | Telecom utility wants a cost-sharing agreement | ROW/Util/RR | No
| RR-8 | QDOT helps City pay for water and sewer-line relocation | ROW/Util/RR | No
| RR-9 | Other utility relocations not completed on time | ROW/Util/RR | No
| RR-10 | Damage existing utility or encounter unanticipated utility during construction | ROW/Util/RR | No
| PR-1 | Uncertainty in construction-cost inflation rate | Procurement | No
| PR-2 | Uncertain Design/Build contracting market conditions at time of bid | Procurement | No
| PR-3 | Material-supply issues | Procurement | No
| PR-4 | Change in project delivery method | Procurement | No
| PR-5 | Accelerate pre-construction activities to reach NTP sooner | Procurement | No
| PR-6 | Use incentives to accelerate D/B construction | Procurement | No
| PR-7 | Issues with D/B design or submittals | Procurement | No
| PR-8 | Other problems with D/B contract procurement | Procurement | No
| CR-1 | D/B construction phasing significantly different than assumed | Construction | No
| CR-2 | Additional Maintenance of Traffic required | Construction | No
| CR-3 | Problems with planned accelerated bridge construction (ABC) technique | Construction | No
| CR-4 | Unable to construct interchange embankments as rapidly as assumed | Construction | No
| CR-5 | Difficult foundation installation | Construction | No
| CR-6 | Severe weather event significantly impacts construction | Construction | No
| CR-7 | Colder-than-usual winter | Construction | No
| CR-8 | Significant accident during construction | Construction | No
| CR-9 | Limited construction staging area in vicinity of interchange | Construction | No
| CR-10 | Fish window in Wandering Creek | Construction | No
| CR-11 | Non-compliance with permits during construction | Construction | No
| CR-12 | Extended overheads as a function of project delays | Construction | No
<===
FWD=>
HOME
Clear All
Create List of Risks
(Ctrl - t)
<=BACK

## 3 - Rating Scale
SHRP2 Risk Management Template
HELP |  |  | Step 03 - Rating Scale
| Base Cost through Construction | 16.04 | (CY $M)
| Base Schedule | 35 | Months
| Base Disruption through Construction | 0.7 | M-Hr
| Data Entry Type | Percent
COST CHANGE
| Adjectival Rating | Percent of Base Cost |  | Absolute Value (CY $M) |  | Expected Mean Value
|  | Low | High | Low | High | Percent | Absolute
| VH | 24.9377 | 49.8753 | 4 | 8 | 37.4065 | 6
| H | 9.9751 | 24.9377 | 1.6 | 4 | 17.4564 | 2.8
| M | 3.1172 | 9.9751 | 0.5 | 1.6 | 6.5461 | 1.05
| L | 1.2469 | 3.1172 | 0.2 | 0.5 | 2.182 | 0.35
| VL | 0 | 1.2469 | 0 | 0.2 | 0.62344 | 0.1
DURATION CHANGE
| Adjectival Rating | Percent of Base Schedule |  | Absolute Value (months) |  | Expected Mean Value
|  | Low | High | Low | High | Percent | Absolute
| VH | 34.2857 | 68.5714 | 12 | 24 | 51.4286 | 18
| H | 11.4286 | 34.2857 | 4 | 12 | 22.8571 | 8
| M | 2.8571 | 11.4286 | 1 | 4 | 7.1429 | 2.5
| L | 0.71429 | 2.8571 | 0.25 | 1 | 1.7857 | 0.625
| VL | 0 | 0.71429 | 0 | 0.25 | 0.35714 | 0.125
DISRUPTION CHANGE
| Adjectival Rating | Percent of Base Disruption |  | Absolute Value (M person-Hrs) |  | Expected Mean Value
|  | Low | High | Low | High | Percent | Absolute
| VH | 28.5714 | 57.1429 | 0.2 | 0.4 | 42.8571 | 0.3
| H | 14.2857 | 28.5714 | 0.1 | 0.2 | 21.4286 | 0.15
| M | 0 | 14.2857 | 0 | 0.1 | 7.1429 | 0.05
| L | 0 | 0 | 0 | 0 | 0 | 0
| VL | 0 | 0 | 0 | 0 | 0 | 0
PROBABILITY OF OCCURRENCE
| Adjectival Rating |  | Probability Range | Mean Probability
|  | Low | High
| VH | 70 | 100 | 85
| H | 40 | 70 | 55
| M | 20 | 40 | 30
| L | 5 | 20 | 12.5
| VL | 0 | 5 | 2.5
<=== BACK
FWD ===>
HOME
Clear All
Create Rating Scale

## 4 - Unmit. Risk Assessment
SHRP2 Risk Management Template
HELP |  |  | Step 04 - Unmitigated Risk Assessment
Risk |  | Probability of Occurrence |  |  |  | Mean Cost Change (CY $M) | [5 empty] | Mean Duration Change (months) |  |  |  |  | Mean Disruption Change (M-Hr)
Label | Risk Description | Adjectival | Numerical | Mean Value | Risk Type | Adjectival | Numerical | Mean Value | Affected Phase | Risk Type | Adjectival | Numerical | Mean Value | Affected Phase | Risk Type | Adjectival | Numerical | Mean Value | Affected Phase
PL-2 | Opposition to removing access to US-555 fro 12th St. | L |  | 12.5 | Threat | VL |  | 0.10025 | Construction |  |  | 0 | 0 |  |  |  | 0 | 0
PL-3 | Opposition to "splitting" alignment of SH-111 in the interchange area. |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
PL-4 | Other stakeholder issues not captured separately. |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
PL-5 | Project funding delayed or reduced. |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
SC-1 | Change in East-West project limits. |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
SC-2 | Change in North-South project limits. |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
SC-3 | Additional local improvements required. | L |  | 12.5 | Threat | L |  | 0.35047 | Construction | Threat | L |  | 0.62475 | Prelim Design/Environmental Process |  |  | 0 | 0
SC-4 | Increased aestethetics for US-555/SH-111 interchange. |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
SC-5 | Replace culvert over Wandering Creek. | M |  | 30 | Threat | L |  | 0.35047 | Construction |  |  | 0 | 0 |  |  |  | 0 | 0
SC-6 | Provide new lighting throughout project. | H |  | 55 | Threat | M |  | 1.0506 | Construction |  |  | 0 | 0 |  |  |  | 0 | 0
SC-7 | ITS added to this project. |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
PD-1 | Shift alignment of US 555 at east end of project | VL |  | 2.5 | Threat | M |  | 1.05 | ROW/Util/RR | Threat | M |  | 2.5 | ROW/Util/RR |  |  | 0 | 0
PD-2 | Split alignment of SH-111 at US-555 interchange. |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
PD-3 | Change in configuration of SH 111 / US 555 interchange. |  | 0 | 0 |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0
PD-4 | Ground improvement required in interchange area. | L |  | 12.5 | Threat | M |  | 1.05 | Construction | Threat | L |  | 0.625 | Construction |  |  | 0 | 0
PD-5 | Shoulders required on US-555. | VL |  | 2.5 | Threat | H |  | 2.8 | Construction | Threat | M |  | 2.5 | Construction |  |  | 0 | 0
PD-6 | Shoulders required on SH-111. | VL |  | 2.5 | Threat | H |  | 2.8 | Construction | Threat | M |  | 2.5 | Construction |  |  | 0 | 0
PD-7 | Additional cost for signalized intersections. |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
PD-8 | Change in pavement section and/or type. | M |  | 30 | Opportunity | M |  | -1.05 | Construction |  |  | 0 | 0 |  |  |  | 0 | 0
PD-9 | Rehabilitate instead of reconstruct existing roadway (e.g., overlay instead). |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
PD-10 | Change in stormwater design standards. |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
PD-11 | Cannot use City sewer system for project runoff (or City charges for use). | M |  | 30 | Threat | M |  | 1.05 | ROW/Util/RR | Threat | L |  | 0.625 | ROW/Util/RR |  |  | 0 | 0
PD-12 | Structures impacted by Main Street realignment are eligible for Historic Register. | L |  | 12.5 | Threat | M |  | 1.05 | ROW/Util/RR | Threat | M |  | 2.5 | ROW/Util/RR |  |  | 0 | 0
PD-13 | Change in environmental documentation. | L |  | 12.5 | Threat | M |  | 1.05 | Prelim Design/Environmental Process | Threat | H |  | 8 | Prelim Design/Environmental Process |  |  | 0 | 0
PD-14 | Delays completing environmental documentation. | M |  | 30 |  |  |  | 0 |  | Threat | M |  | 2.5 | Prelim Design/Environmental Process |  |  | 0 | 0
PD-15 | Encounter unanticipated contamination in interchange area. | M |  | 30 | Threat | VL |  | 0.1 | Construction |  |  | 0 | 0 |  |  |  | 0 | 0
PD-16 | Additional wetland mitigation required for planned alignment. | M |  | 30 | Threat | L |  | 0.35 | Construction |  |  | 0 | 0 |  |  |  | 0 | 0
EP-1 | Challenge to environmental determination or permits |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
EP-2 | Delay obtaining the 404 permit | L |  | 12.5 |  |  |  | 0 |  | Threat | M |  | 2.5 | Environmental Permits |  |  | 0 | 0
RR-1 | Uncertainty in ROW inflation rate | H |  | 55 | Threat | M |  | 1.05 | ROW/Util/RR |  |  | 0 | 0 |  |  |  | 0 | 0
RR-2 | Accelerating pace of development in interchange area | M |  | 30 | Threat | M |  | 1.05 | ROW/Util/RR | Threat | M |  | 2.5 | ROW/Util/RR |  |  | 0 | 0
RR-3 | Unwilling sellers | H |  | 55 | Threat | M |  | 1.05 | ROW/Util/RR |  |  | 0 | 0 |  |  |  | 0 | 0
RR-4 | Additional relocation or demolition required |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
RR-5 | Additional ROW required for planned project |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
RR-6 | Other delays to ROW planning | M |  | 30 |  |  |  | 0 |  | Threat | L |  | 0.625 | ROW/Util/RR |  |  | 0 | 0
RR-7 | Telecom utility wants a cost-sharing agreement | M |  | 30 | Threat | L |  | 0.35 | ROW/Util/RR |  |  | 0 | 0 |  |  |  | 0 | 0
RR-8 | QDOT helps City pay for water and sewer-line relocation | H |  | 55 | Threat | M |  | 1.05 | ROW/Util/RR |  |  | 0 | 0 |  |  |  | 0 | 0
RR-9 | Other utility relocations not completed on time |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
RR-10 | Damage existing utility or encounter unanticipated utility during construction |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
PR-1 | Uncertainty in construction-cost inflation rate | H |  | 55 | Threat | M |  | 1.05 | Construction |  |  | 0 | 0 |  |  |  | 0 | 0
PR-2 | Uncertain Design/Build contracting market conditions at time of bid |  | 25 | 25 | Threat |  | 1.185 | 1.185 | Construction | Threat |  | 1 | 1 | Procurement |  |  | 0 | 0
PR-3 | Material-supply issues |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
PR-4 | Change in project delivery method |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
PR-5 | Accelerate pre-construction activities to reach NTP sooner |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
PR-6 | Use incentives to accelerate D/B construction |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
PR-7 | Issues with D/B design or submittals | M |  | 30 |  |  |  | 0 |  | Threat | M |  | 2.5 | Final Design |  |  | 0 | 0
PR-8 | Other problems with D/B contract procurement | L |  | 12.5 |  |  |  | 0 |  | Threat | L |  | 0.625 | Procurement |  |  | 0 | 0
CR-1 | D/B construction phasing significantly different than assumed |  | 25 | 25 |  |  |  | 0 |  | Opportunity |  | 2 | -2 | Construction | Opportunity |  | 0.1 | -0.1 | Construction
CR-2 | Additional Maintenance of Traffic required | H |  | 55 | Threat | L |  | 0.35 | Construction | Threat | VL |  | 0.125 | Construction | Threat | M |  | 0.05 | Construction
CR-3 | Problems with planned accelerated bridge construction (ABC) technique | H |  | 55 | Threat | L |  | 0.35 | Construction | Threat | L |  | 0.625 | Construction | Threat | L |  | 0 | Construction
CR-4 | Unable to construct interchange embankments as rapidly as assumed | M |  | 30 | Threat | L |  | 0.35 | Construction | Threat | M |  | 2.5 | Construction |  | L |  | 0 | Construction
CR-5 | Difficult foundation installation | L |  | 12.5 | Threat | L |  | 0.35 | Construction | Threat | L |  | 0.625 | Construction | Threat | VL |  | 0 | Construction
CR-6 | Severe weather event significantly impacts construction |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
CR-7 | Colder-than-usual winter | L |  | 12.5 |  |  |  | 0 |  | Threat | VL |  | 0.125 | Construction | Threat | VL |  | 0 | Construction
CR-8 | Significant accident during construction |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
CR-9 | Limited construction staging area in vicinity of interchange | M |  | 30 | Threat | VL |  | 0.1 | Construction |  |  | 0 | 0 |  |  |  | 0 | 0
CR-10 | Fish window in Wandering Creek |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
CR-11 | Non-compliance with permits during construction |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
CR-12 | Extended overheads as a function of project delays |  |  | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
<=== BACK
FWD===>
HOME
Conduct Risk
Assessment
Clear All
Calculate Mean
Severity Values

## 5 - Unmit. Risk Register
SHRP2 Risk Management Template
HELP |  | Step 05 - Unmitigated Risk Register
NOTE: Risks and opportunities are sorted by total severity, though the order should be identical whether using raw severity or percent of total severity
Risk Label | Risk Description | Risk Type | Mean Cost Impact (CY $M) | Mean Duration Impact (months) | Mean Disruption Impact (M-Hr) | Mean Change to Critical Path Schedule | Mean Severity (YOE $M) | Percent of Total Severity | Risk Ranking based on Mean Severity | Select Risk for Mitigation
SC-6 | Provide new lighting throughout project. | Threat | 0.57784 | 0 | 0 | 0 | 0.61753 | 8.321% | 1 | Yes | 0.61753 | SC
PR-1 | Uncertainty in construction-cost inflation rate | Threat | 0.5775 | 0 | 0 | 0 | 0.61716 | 8.316% | 2 | Yes | 0.61716 | PR
RR-1 | Uncertainty in ROW inflation rate | Threat | 0.5775 | 0 | 0 | 0 | 0.60365 | 8.134% | 3 | No | 0.60365 | RR
RR-3 | Unwilling sellers | Threat | 0.5775 | 0 | 0 | 0 | 0.60365 | 8.134% | 4 | Yes | 0.60365 | RR
RR-8 | QDOT helps City pay for water and sewer-line relocation | Threat | 0.5775 | 0 | 0 | 0 | 0.60365 | 8.134% | 5 | Yes | 0.60365 | RR
RR-2 | Accelerating pace of development in interchange area | Threat | 0.315 | 0.75 | 0 | 0.75 | 0.51205 | 6.9% | 6 | Yes | 0.51205 | RR
CR-2 | Additional Maintenance of Traffic required | Threat | 0.1925 | 0.06875 | 0.0275 | 0.06875 | 0.50631 | 6.822% | 7 | Yes | 0.50631 | CR
CR-4 | Unable to construct interchange embankments as rapidly as assumed | Threat | 0.105 | 0.75 | 0 | 0.75 | 0.39151 | 5.275% | 8 | Yes | 0.39151 | CR
PD-13 | Change in environmental documentation. | Threat | 0.13125 | 1 | 0 | 1 | 0.37949 | 5.113% | 9 | No | 0.37949 | PD
PR-2 | Uncertain Design/Build contracting market conditions at time of bid | Threat | 0.29625 | 0.25 | 0 | 0.25 | 0.37535 | 5.058% | 10 | No | 0.37535 | PR
PD-11 | Cannot use City sewer system for project runoff (or City charges for use). | Threat | 0.315 | 0.1875 | 0 | 0.1875 | 0.37493 | 5.052% | 11 | Yes | 0.37493 | PD
CR-3 | Problems with planned accelerated bridge construction (ABC) technique | Threat | 0.1925 | 0.34375 | 0 | 0.34375 | 0.33372 | 4.497% | 12 | Yes | 0.33372 | CR
PD-12 | Structures impacted by Main Street realignment are eligible for Historic Register. | Threat | 0.13125 | 0.3125 | 0 | 0.3125 | 0.21316 | 2.872% | 13 | No | 0.21316 | PD
PD-14 | Delays completing environmental documentation. | Threat | 0 | 0.75 | 0 | 0.75 | 0.18441 | 2.485% | 14 | Yes | 0.18441 | PD
PD-4 | Ground improvement required in interchange area. | Threat | 0.13125 | 0.078125 | 0 | 0.078125 | 0.16933 | 2.282% | 15 | No | 0.16933 | PD
SC-5 | Replace culvert over Wandering Creek. | Threat | 0.10514 | 0 | 0 | 0 | 0.11236 | 1.514% | 16 | No | 0.11236 | SC
PD-16 | Additional wetland mitigation required for planned alignment. | Threat | 0.105 | 0 | 0 | 0 | 0.11221 | 1.512% | 17 | No | 0.11221 | PD
RR-7 | Telecom utility wants a cost-sharing agreement | Threat | 0.105 | 0 | 0 | 0 | 0.10975 | 1.479% | 18 | No | 0.10975 | RR
PD-5 | Shoulders required on US-555. | Threat | 0.07 | 0.0625 | 0 | 0.0625 | 0.09805 | 1.321% | 19 | No | 0.09805 | PD
PD-6 | Shoulders required on SH-111. | Threat | 0.07 | 0.0625 | 0 | 0.0625 | 0.09805 | 1.321% | 20 | No | 0.09805 | PD
CR-5 | Difficult foundation installation | Threat | 0.04375 | 0.078125 | 0 | 0.078125 | 0.075803 | 1.021% | 21 | No | 0.075803 | CR
EP-2 | Delay obtaining the 404 permit | Threat | 0 | 0.3125 | 0 | 0.3125 | 0.073452 | 0.9897% | 22 | No | 0.073452 | EP
SC-3 | Additional local improvements required. | Threat | 0.043809 | 0.078094 | 0 | 0.078094 | 0.066004 | 0.8894% | 23 | No | 0.066004 | SC
RR-6 | Other delays to ROW planning | Threat | 0 | 0.1875 | 0 | 0.1875 | 0.045513 | 0.6133% | 24 | No | 0.045513 | RR
PD-1 | Shift alignment of US 555 at east end of project | Threat | 0.02625 | 0.0625 | 0 | 0.0625 | 0.042611 | 0.5742% | 25 | No | 0.042611 | PD
PD-15 | Encounter unanticipated contamination in interchange area. | Threat | 0.03 | 0 | 0 | 0 | 0.03206 | 0.432% | 26 | No | 0.03206 | PD
CR-9 | Limited construction staging area in vicinity of interchange | Threat | 0.03 | 0 | 0 | 0 | 0.03206 | 0.432% | 27 | No | 0.03206 | CR
PR-8 | Other problems with D/B contract procurement | Threat | 0 | 0.078125 | 0 | 0.078125 | 0.018358 | 0.2474% | 28 | No | 0.018358 | PR
PL-2 | Opposition to removing access to US-555 fro 12th St. | Threat | 0.012531 | 0 | 0 | 0 | 0.013392 | 0.1804% | 29 | No | 0.013392 | PL
CR-7 | Colder-than-usual winter | Threat | 0 | 0.015625 | 0 | 0.015625 | 0.0058071 | 0.07825% | 30 | No | 0.0058071 | CR
CR-1 | D/B construction phasing significantly different than assumed | Opportunity | 0 | -0.5 | -0.025 | -0.5 | -0.43567 | 56.41% | 1 | No | 0.43567 | CR
PD-8 | Change in pavement section and/or type. | Opportunity | -0.315 | 0 | 0 | 0 | -0.33663 | 43.59% | 2 | No | 0.33663 | PD
PL-3 | Opposition to "splitting" alignment of SH-111 in the interchange area. | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | PL
PL-4 | Other stakeholder issues not captured separately. | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | PL
PL-5 | Project funding delayed or reduced. | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | PL
SC-1 | Change in East-West project limits. | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | SC
SC-2 | Change in North-South project limits. | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | SC
SC-4 | Increased aestethetics for US-555/SH-111 interchange. | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | SC
SC-7 | ITS added to this project. | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | SC
PD-2 | Split alignment of SH-111 at US-555 interchange. | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | PD
PD-3 | Change in configuration of SH 111 / US 555 interchange. | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | PD
PD-7 | Additional cost for signalized intersections. | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | PD
PD-9 | Rehabilitate instead of reconstruct existing roadway (e.g., overlay instead). | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | PD
PD-10 | Change in stormwater design standards. | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | PD
EP-1 | Challenge to environmental determination or permits | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | EP
RR-4 | Additional relocation or demolition required | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | RR
RR-5 | Additional ROW required for planned project | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | RR
RR-9 | Other utility relocations not completed on time | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | RR
RR-10 | Damage existing utility or encounter unanticipated utility during construction | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | RR
PR-3 | Material-supply issues | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | PR
PR-4 | Change in project delivery method | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | PR
PR-5 | Accelerate pre-construction activities to reach NTP sooner | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | PR
PR-6 | Use incentives to accelerate D/B construction | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | PR
PR-7 | Issues with D/B design or submittals | No Impact | 0 | 0.75 | 0 | 0 | 0 | 0% |  | No | 0 | PR
CR-6 | Severe weather event significantly impacts construction | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | CR
CR-8 | Significant accident during construction | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | CR
CR-10 | Fish window in Wandering Creek | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | CR
CR-11 | Non-compliance with permits during construction | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | CR
CR-12 | Extended overheads as a function of project delays | No Impact | 0 | 0 | 0 | 0 | 0 | 0% |  | No | 0 | CR
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
<=== BACK
L
FWD ===>
HOME

## 6 - Unmit. Project Performance
SHRP2 Risk Management Template
HELP |  |  | Step 06 - Unmitigated Project Performance
Schedule Duration Assumption:
Some risks in a phase will occur concurrently, while others will occur sequentially.
Unmitigated Project Cost, Duration, and Disruption Performance
Project Phase | Base |  |  |  | Risk |  |  | Total (Base + Risk)
| Cost (CY $M) | Duration (months) | Disruption (M-hrs) | Cost (CY $M) | Duration (months) | Disruption (M-hrs) | Cost (CY $M) | Duration (months) | Disruption (M-hrs) | Cost (YOE $M)
Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scoping |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prelim Design/Environmental Process | 1.19 | 12 | 0 | 0.13125 | 1.414 | 0 | 1.3213 | 13.414 | 0 | 1.3432
Environmental Permits |  | 6 | 0 | 0 | 0.3125 | 0 | 0 | 6.3125 | 0 | 0
ROW/Util/RR | 3 | 12 | 0.2 | 2.625 | 1.125 | 0 | 5.625 | 13.125 | 0.2 | 5.9084
Final Design |  | 6 | 0 | 0 | 0.75 | 0 | 0 | 6.75 | 0 | 0
Procurement |  | 6 | 0 | 0.2539 | 0.28906 | 0 | 0.2539 | 6.2891 | 0 | 0.26473
Construction | 11.85 | 16 | 0.5 | 2.4604 | 0.85469 | 0.0025 | 14.3104 | 16.8547 | 0.5025 | 15.4052
Operations & Maintenance | 0 | 600 | 1.4 | 0 | 0 | 0 | 0 | 600 | 1.4
Replacement | 0 | 0 | 0.7 | 0 |  | 0 | 0 | 0 | 0.7
Total | 16.04 |  | 2.8 | 5.4705 |  | 0.0025 | 21.5105 |  | 2.8025 | 22.9216
Project Schedule Performance (Base vs. Unmitigated)
Project Phase |  |  | Base Project Schedule Performance | [5 empty] | Unmitigated Project Schedule Performance |  |  |  | Mean
| Duration (Months/Date) | Early Start | Early Finish | Late Start | Late Finish | Float (months) | Duration (Months / Date) | Early Start | Early Finish | Late Start | Late Finish | Float (months) | Severity YOE ($M)
Planning | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | 0.013392
Scoping | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | 0.7959
Design Funding Date | 4014800% |  | 4014800% |  | 4014800% | 0 | 4014800% |  | 4014800% |  | 4014800% | 0 | 0
Prelim Design/Environmental Process | 12 | 4014800% | 4051280% | 4014800% | 4051280% | 0 | 13.414 | 4014800% | 4055579% | 4014800% | 4055579% | 0 | 1.3677
Environmental Permits | 6 | 4051280% | 4069520% | 4051280% | 4069520% | 0 | 6.3125 | 4055579% | 4074769% | 4058049% | 4077239% | 0.8125 | 0.073452
ROW/Util/RR Funding Date | 4014800% |  | 4014800% |  | 4087760% | 24 | 4014800% |  | 4014800% |  | 4095479% | 26.539 | 0
ROW/Util/RR | 12 | 4051280% | 4087760% | 4051280% | 4087760% | 0 | 13.125 | 4055579% | 4095479% | 4055579% | 4095479% | 0 | 2.4783
Construction Funding Date | 4014800% |  | 4014800% |  | 4051280% | 12 | 4014800% |  | 4014800% |  | 4058120% | 14.25 | 0
Procurement | 6 | 4051280% | 4069520% | 4051280% | 4069520% | 0 | 6.2891 | 4055579% | 4077239% | 4058120% | 4077239% | 0 | 1.0109
Final Design | 6 | 4069520% | 4087760% | 4069520% | 4102960% | 5 | 6.75 | 4077239% | 4097759% | 4077239% | 4113277% | 5.1047 | 0
Construction | 16 | 4072560% | 4121200% | 4072560% | 4121200% | 0 | 16.8547 | 4080279% | 4131517% | 4080279% | 4131517% | 0 | 0.90955
Operations & Maintenance | 600 | 4121200% | 5945200% | 4121200% | 5945200% |  | 600 | 4131517% | 5955517% | 4131517% | 5955517%
Replacement | 0 | 5945200% | 5945200% | 5945200% | 5945200% |  | 0 | 5955517% | 5955517% | 5955517% | 5955517%
Project Start Date | 4014800% | [5 empty] | 4014800% |  |  |  |  | Total | 6.6491
Construction Finish Date | 4121200% | [5 empty] | 4131517%
Project Duration (months) | 35 | [5 empty] | 38.3937
<==BACK
FWD==>
HOME
Create Risk Analysis Summary
Makes sure you click on "Calculate Mean Severity Value" on Step 4 before running the Risk Analysis

## 7 - Unmit. Risk Ranking Plots
SHRP2 Risk Management Template
HELP | Step 07 - Unmitigated Risk Ranking Plots
<==BACK
FWD==>
HOME

## 8 - Risk Mitigation Strategies
SHRP2 Risk Management Template
HELP |  |  |  |  | Step 08 - Risk Mitigation Strategies
Risk Mitigation Label | Risk Mitigation Actions |  | Implementation Needs of Risk Mitigation Actions | [8 empty] | Consequences of Risk Mitigation Actions |  |  |  | Effectiveness of Risk Mitigation Actions |  |  |  |  | Mitigated Severity |  |  |  | Risk Mitigation Consequences Performance | [5 empty] | Unmitigated Severity
|  | Cost |  | Schedule |  | Disruption |  | New | Probability |  |  | Percentage Mitigated, if implemented
|  | Mean Cost (CY $M) | Affected Phase | Mean Duration (months) | Affected Phase | Mean Disruption (M-Hr) | Affected Phase | Adjectival (VL, L, M, H, VH) | Numerical (%) | Cost (%) | Mean Cost (CY $M) | Duration (%) | Mean Duration (months) | Disruption (%) | Mean Disruption (M-Hr) | Mitigated Severity (%) | Benefit/Cost Ratio | Action Selected | Mean Cost Change (YOE $M) | Mean Duration Change (YOE $M) | Mean Disruption Change (YOE $M) | Mean Change to Crit. Path (YOE $M) | Mean Severity (YOE $M) | Cost (CY $M) | Duration (Months) | Disruption (M-Hr) | Mean change to critical path | Mean Severity (YOE $M) | Mean Cost Change (YOE $M) | Mean Duration Change (YOE $M) | Mean Disruption Change (YOE $M) | Mean Change to Crit. Path (YOE $M) | Mean Severity (YOE $M)
SC-6 | Provide new lighting throughout project.
SC-6_1 | Do Nothing | [7 empty] | 55 | 0 | 1.05062 | 0 | 0 | 0 | 0 |  |  | No | [14 empty] | 0.61753
SC-6_2 | Negotiate cost sharing agreement with the city | 0 | Construction | 0 | Construction | 0 | Construction |  | 55 | 50 | 0.28892 |  | 0 |  | 0 | 50 | No Cost | Yes | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0.30876 | 0 | 0 | 0 | 0.30876 | 0 | 0 | 0 | 0 | 0 | 0.28892 | 0 | 0 | 0 | 0.30876
SC-6_3 | [17 empty] | No | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0.00264 | 2.7 | 0 | 2.7 | 0.17114
SC-6_4 | [17 empty] | No | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SC-6_5 | [17 empty] | No
RR-3 | Unwilling sellers
RR-3_1 | Do Nothing | [7 empty] | 55 | 0 | 1.05 | 0 | 0 | 0 | 0 |  |  | No | [14 empty] | 0.60365
RR-3_2 | Make reasonable early offer | 0.05 | ROW/Util/RR | 0 | ROW/Util/RR | 0 | ROW/Util/RR |  | 27.5 |  | 0.28875 |  | 0 |  | 0 | 50 | 5.775 | Yes | 0.052264 | 0 | 0 | 0 | 0.052264 | [5 empty] | 0.30182 | 0 | 0 | 0 | 0.30182 | 0.05 | 0 | 0 | 0 | 0.052264 | 0.28875 | 0 | 0 | 0 | 0.30182
RR-3_3 | [17 empty] | No
RR-3_4 | [17 empty] | No
RR-3_5 | [17 empty] | No
CR-2 | Additional Maintenance of Traffic required
CR-2_1 | Do Nothing | [7 empty] | 55 | 0 | 0.35 | 0 | 0.125 | 0 | 0.05 |  |  | No | [14 empty] | 0.50668
CR-2_2 | Reduce traffic demand during closures | 0.05 | Final Design | 0 | Final Design | 0 | Construction |  | 27.5 |  | 0.09625 |  | 0.034375 | 67 | 0.0045375 | 68.1841 | 6.5616 | Yes | 0.052651 | 0 | 0 | 0 | 0.052651 | [5 empty] | 0.10286 | 0.0010811 | 0.045375 | 0.00845 | 0.1612 | 0.05 | 0 | 0 | 0 | 0.052651 | 0.09625 | 0.034375 | 0.0045375 | 0.034375 | 0.1612
CR-2_3 | [17 empty] | No
CR-2_4 | [17 empty] | No
CR-2_5 | [17 empty] | No
RR-2 | Accelerating pace of development in interchange area
RR-2_1 | Do Nothing | [7 empty] | 30 | 0 | 1.05 | 0 | 2.5 | 0 | 0 |  |  | No | [14 empty] | 0.51205
RR-2_2 | Coordinate with City - stop issuing permits for new developments | 0 | ROW/Util/RR | 0 | ROW/Util/RR | 0 | ROW/Util/RR |  | 15 |  | 0.1575 |  | 0.375 |  | 0 | 50.0381 | No Cost | Yes | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0.16463 | 0.0030501 | 0 | 0.050649 | 0.25583 | 0 | 0 | 0 | 0 | 0 | 0.1575 | 0.375 | 0 | 0.375 | 0.25583
RR-2_3 | [17 empty] | No
RR-2_4 | [17 empty] | No
RR-2_5 | [17 empty] | No
PD-11 | Cannot use City sewer system for project runoff (or City charges for use).
PD-11_1 | Do Nothing | [7 empty] | 30 | 0 | 1.05 | 0 | 0.625 | 0 | 0 |  |  | No | [14 empty] | 0.37493
PD-11_2 | Same action as RR8 (affects RR8 and PD11) | 0 | Final Design | 0 | Final Design | 0 | Final Design |  | 15 |  | 0.1575 |  | 0.09375 |  | 0 | 50.0109 | No Cost | Yes | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0.16463 | 0.00076226 | 0 | 0.012654 | 0.18742 | 0 | 0 | 0 | 0 | 0 | 0.1575 | 0.09375 | 0 | 0.09375 | 0.18742
PD-11_3 | [17 empty] | No
PD-11_4 | [17 empty] | No
PD-11_5 | [17 empty] | No
RR-8 | QDOT helps City pay for water and sewer-line relocation
RR-8_1 | Do Nothing | [7 empty] | 55 | 0 | 1.05 | 0 | 0 | 0 | 0 |  |  | No | [14 empty] | 0.60365
RR-8_2 | Decide to help city pay for water and sewer line relocation | 0 | Construction | 0 | Construction | 0 | Construction |  | 86.5 |  | 0.90825 |  | 0 |  | 0 | -57.2727 | No Cost | Yes | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0.94937 | 0 | 0 | 0 | 0.94937 | 0 | 0 | 0 | 0 | 0 | 0.90825 | 0 | 0 | 0 | 0.94937
RR-8_3 | [17 empty] | No | [15 empty] | 0.05 | 0 | 0 | 0 | 0.053434 | 0.1925 | 0.34375 | 0 | 0.34375 | 0.33556
RR-8_4 | [17 empty] | No
RR-8_5 | [17 empty] | No
CR-4 | Unable to construct interchange embankments as rapidly as assumed
CR-4_1 | Do Nothing | [7 empty] | 30 | 0 | 0.35 | 0 | 2.5 | 0 | 0 |  |  | No | [14 empty] | 0.39552
CR-4_2 | Conduct additional investigations and analysis to develop at techniques | 0.1 | Final Design | 0 | Final Design | 0 | Construction |  | 15 |  | 0.0525 |  | 0.375 |  | 0 | 50.036 | 1.8794 | Yes | 0.1053 | 0 | 0 | 0 | 0.1053 | [5 empty] | 0.056106 | 0.011755 | 0 | 0.092259 | 0.19762 | 0.1 | 0 | 0 | 0 | 0.1053 | 0.0525 | 0.375 | 0 | 0.375 | 0.19762
CR-4_3 | [17 empty] | No
CR-4_4 | [17 empty] | No
CR-4_5 | [17 empty] | No
CR-3 | Problems with planned accelerated bridge construction (ABC) technique
CR-3_1 | Do Nothing | [7 empty] | 55 | 0 | 0.35 | 0 | 0.625 | 0 | 0 |  |  | No | [14 empty] | 0.33556
CR-3_2 | Pre-qualify contractors + require development of ABC technique | 0.05 | Final Design | 0 | Final Design | 0 | Construction |  | 27.5 |  | 0.09625 |  | 0.17188 |  | 0 | 50.0187 | 3.1878 | Yes | 0.052651 | 0 | 0 | 0 | 0.052651 | [5 empty] | 0.10286 | 0.0054062 | 0 | 0.042264 | 0.16772 | 0.05 | 0 | 0 | 0 | 0.052651 | 0.09625 | 0.17188 | 0 | 0.17187 | 0.16772
CR-3_3 | [17 empty] | No
CR-3_4 | [17 empty] | No
CR-3_5 | [17 empty] | No
[34 empty] | 0.01 | 0 | 0 | 0 | 0.010404 | 0 | 0 | 0 | 0 | 0
<===BACK
FWD==>
HOME
Conduct Risk Mitigation
Clear All
Create Registers

## 9 - Mit. Strategies Register
SHRP2 Risk Management Template
HELP |  |  |  | Step 09 - Mitigation Strategies Register
NOTE: The order of the risks here is similar to the order of the
risks selected for mitigation in Step 05- Unmitigated Risk Register
|  | Risk | Risk Mitigation |  |  | Implementation Effort |  |  |  |  | Mitigated Risk Effort |  |  | Effectiveness of Mitigation Actions
Risk | Risk Description | Mitigation | Action Description
Label |  | Label |  | Mean Cost Change (YOE $M) | Mean Duration Change (YOE $M) | Mean Disruption Change (YOE $M) | Mean Change to Crit. Path (YOE $M) | Mean Severity (YOE $M) | Mean Cost Change (YOE $M) | Mean Duration Change (YOE $M) | Mean Disruption Change (YOE $M) | Mean Change to Crit. Path (YOE $M) | Mean Severity (YOE $M) | Mitigated Severity % | Benefit/Cost Ratio | Responsibility | Schedule /Milestone | Comments
SC-6 | Provide new lighting throughout project. | SC-6_2 | Negotiate cost sharing agreement with the city | 0 | 0 | 0 | 0 | 0 | 0.28892 | 0 | 0 | 0 | 0.30876 | 50 | No Cost | Project Director | Midway thru prelim design
RR-3 | Unwilling sellers | RR-3_2 | Make reasonable early offer | 0.05 | 0 | 0 | 0 | 0.052264 | 0.28875 | 0 | 0 | 0 | 0.30182 | 50 | 5.775 | Project Engineer | Midway thru ROW/Util/RR
CR-2 | Additional Maintenance of Traffic required | CR-2_2 | Reduce traffic demand during closures | 0.05 | 0 | 0 | 0 | 0.052651 | 0.09625 | 0.034375 | 0.0045375 | 0.034375 | 0.1612 | 68.1841 | 6.5616 | Project Engineer | Midway thru final design
RR-2 | Accelerating pace of development in interchange area | RR-2_2 | Coordinate with City - stop issuing permits for new developments | 0 | 0 | 0 | 0 | 0 | 0.1575 | 0.375 | 0 | 0.375 | 0.25583 | 50.0381 | No Cost | Project Engineer | Midway thru prelim design
PD-11 | Cannot use City sewer system for project runoff (or City charges for use). | PD-11_2 | Same action as RR8 (affects RR8 and PD11) | 0 | 0 | 0 | 0 | 0 | 0.1575 | 0.09375 | 0 | 0.09375 | 0.18742 | 50.0109 | No Cost | Project Engineer | Midway thru prelim design
RR-8 | QDOT helps City pay for water and sewer-line relocation | RR-8_2 | Decide to help city pay for water and sewer line relocation | 0 | 0 | 0 | 0 | 0 | 0.90825 | 0 | 0 | 0 | 0.94937 | -57.2727 | No Cost
CR-4 | Unable to construct interchange embankments as rapidly as assumed | CR-4_2 | Conduct additional investigations and analysis to develop at techniques | 0.1 | 0 | 0 | 0 | 0.1053 | 0.0525 | 0.375 | 0 | 0.375 | 0.19762 | 50.036 | 1.8794 | Project Engineer | Midway thru final design
CR-3 | Problems with planned accelerated bridge construction (ABC) technique | CR-3_2 | Pre-qualify contractors + require development of ABC technique | 0.05 | 0 | 0 | 0 | 0.052651 | 0.09625 | 0.17188 | 0 | 0.17187 | 0.16772 | 50.0187 | 3.1878 | Project Engineer | Midway thru final design
<===BACK
HOME
FWD===>

## 10 - Mit. Risk Register
SHRP2 Risk Management Template
HELP |  |  | Step 10 - Mitigated Risk Register
NOTE: Risks and opportunities are sorted by total severity, though the order should be identical whether using raw severity or percent of total severity
Risk Label | Risk Description | Risk Type | Mean Cost Impact (CY $M) | Mean Duration Impact (months) | Mean Disruption Impact (M-Hr) | Mean Change to Critical Path Schedule | Mean Severity (YOE $M) | Percent of Total Mean Severity | Risk Ranking based on Mean Severity | Retire Risk ?
RR-8 | QDOT helps City pay for water and sewer-line relocation | Threat | 0.90825 | 0 | 0 | 0 | 0.94937 | 0.15798 | 1 | No | 0.94937 | RR
PR-1 | Uncertainty in construction-cost inflation rate | Threat | 0.5775 | 0 | 0 | 0 | 0.61716 | 0.1027 | 2 | No | 0.61716 | PR
RR-1 | Uncertainty in ROW inflation rate | Threat | 0.5775 | 0 | 0 | 0 | 0.60365 | 0.10045 | 3 | No | 0.60365 | RR
PD-13 | Change in environmental documentation. | Threat | 0.13125 | 1 | 0 | 1 | 0.37949 | 0.063149 | 4 | No | 0.37949 | PD
PR-2 | Uncertain Design/Build contracting market conditions at time of bid | Threat | 0.29625 | 0.25 | 0 | 0.25 | 0.37535 | 0.062461 | 5 | No | 0.37535 | PR
SC-6 | Provide new lighting throughout project. | Threat | 0.28892 | 0 | 0 | 0 | 0.30876 | 0.05138 | 6 | No | 0.30876 | SC
RR-3 | Unwilling sellers | Threat | 0.28875 | 0 | 0 | 0 | 0.30182 | 0.050225 | 7 | No | 0.30182 | RR
RR-2 | Accelerating pace of development in interchange area | Threat | 0.1575 | 0.375 | 0 | 0.375 | 0.25583 | 0.042572 | 8 | No | 0.25583 | RR
PD-12 | Structures impacted by Main Street realignment are eligible for Historic Register. | Threat | 0.13125 | 0.3125 | 0 | 0.3125 | 0.21316 | 0.035472 | 9 | No | 0.21316 | PD
CR-4 | Unable to construct interchange embankments as rapidly as assumed | Threat | 0.0525 | 0.375 | 0 | 0.375 | 0.19762 | 0.032885 | 10 | No | 0.19762 | CR
PD-11 | Cannot use City sewer system for project runoff (or City charges for use). | Threat | 0.1575 | 0.09375 | 0 | 0.09375 | 0.18742 | 0.031188 | 11 | No | 0.18742 | PD
PD-14 | Delays completing environmental documentation. | Threat | 0 | 0.75 | 0 | 0.75 | 0.18441 | 0.030687 | 12 | No | 0.18441 | PD
PD-4 | Ground improvement required in interchange area. | Threat | 0.13125 | 0.078125 | 0 | 0.078125 | 0.16975 | 0.028247 | 13 | No | 0.16975 | PD
CR-3 | Problems with planned accelerated bridge construction (ABC) technique | Threat | 0.09625 | 0.17188 | 0 | 0.17187 | 0.16772 | 0.027909 | 14 | No | 0.16772 | CR
CR-2 | Additional Maintenance of Traffic required | Threat | 0.09625 | 0.034375 | 0.0045375 | 0.034375 | 0.1612 | 0.026825 | 15 | No | 0.1612 | CR
SC-5 | Replace culvert over Wandering Creek. | Threat | 0.10514 | 0 | 0 | 0 | 0.11236 | 0.018698 | 16 | No | 0.11236 | SC
PD-16 | Additional wetland mitigation required for planned alignment. | Threat | 0.105 | 0 | 0 | 0 | 0.11221 | 0.018673 | 17 | No | 0.11221 | PD
RR-7 | Telecom utility wants a cost-sharing agreement | Threat | 0.105 | 0 | 0 | 0 | 0.10975 | 0.018264 | 18 | No | 0.10975 | RR
PD-5 | Shoulders required on US-555. | Threat | 0.07 | 0.0625 | 0 | 0.0625 | 0.098384 | 0.016372 | 19 | No | 0.098384 | PD
PD-6 | Shoulders required on SH-111. | Threat | 0.07 | 0.0625 | 0 | 0.0625 | 0.098384 | 0.016372 | 20 | No | 0.098384 | PD
CR-5 | Difficult foundation installation | Threat | 0.04375 | 0.078125 | 0 | 0.078125 | 0.07622 | 0.012683 | 21 | No | 0.07622 | CR
EP-2 | Delay obtaining the 404 permit | Threat | 0 | 0.3125 | 0 | 0.3125 | 0.073452 | 0.012223 | 22 | No | 0.073452 | EP
SC-3 | Additional local improvements required. | Threat | 0.043809 | 0.078094 | 0 | 0.078094 | 0.066004 | 0.010983 | 23 | No | 0.066004 | SC
RR-6 | Other delays to ROW planning | Threat | 0 | 0.1875 | 0 | 0.1875 | 0.045513 | 0.0075736 | 24 | No | 0.045513 | RR
PD-1 | Shift alignment of US 555 at east end of project | Threat | 0.02625 | 0.0625 | 0 | 0.0625 | 0.042611 | 0.0070908 | 25 | No | 0.042611 | PD
PD-15 | Encounter unanticipated contamination in interchange area. | Threat | 0.03 | 0 | 0 | 0 | 0.03206 | 0.0053351 | 26 | No | 0.03206 | PD
CR-9 | Limited construction staging area in vicinity of interchange | Threat | 0.03 | 0 | 0 | 0 | 0.03206 | 0.0053351 | 27 | No | 0.03206 | CR
PR-8 | Other problems with D/B contract procurement | Threat | 0 | 0.078125 | 0 | 0.078125 | 0.018358 | 0.0030548 | 28 | No | 0.018358 | PR
PL-2 | Opposition to removing access to US-555 fro 12th St. | Threat | 0.012531 | 0 | 0 | 0 | 0.013392 | 0.0022285 | 29 | No | 0.013392 | PL
CR-7 | Colder-than-usual winter | Threat | 0 | 0.015625 | 0 | 0.015625 | 0.0058906 | 0.00098024 | 30 | No | 0.0058906 | CR
CR-1 | D/B construction phasing significantly different than assumed | Opportunity | 0 | -0.5 | -0.025 | -0.5 | -0.43833 | 0.56562 | 1 | No | 0.43833 | CR
PD-8 | Change in pavement section and/or type. | Opportunity | -0.315 | 0 | 0 | 0 | -0.33663 | 0.43438 | 2 | No | 0.33663 | PD
PL-3 | Opposition to "splitting" alignment of SH-111 in the interchange area. | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | PL
PL-4 | Other stakeholder issues not captured separately. | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | PL
PL-5 | Project funding delayed or reduced. | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | PL
SC-1 | Change in East-West project limits. | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | SC
SC-2 | Change in North-South project limits. | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | SC
SC-4 | Increased aestethetics for US-555/SH-111 interchange. | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | SC
SC-7 | ITS added to this project. | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | SC
PD-2 | Split alignment of SH-111 at US-555 interchange. | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | PD
PD-3 | Change in configuration of SH 111 / US 555 interchange. | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | PD
PD-7 | Additional cost for signalized intersections. | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | PD
PD-9 | Rehabilitate instead of reconstruct existing roadway (e.g., overlay instead). | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | PD
PD-10 | Change in stormwater design standards. | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | PD
EP-1 | Challenge to environmental determination or permits | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | EP
RR-4 | Additional relocation or demolition required | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | RR
RR-5 | Additional ROW required for planned project | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | RR
RR-9 | Other utility relocations not completed on time | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | RR
RR-10 | Damage existing utility or encounter unanticipated utility during construction | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | RR
PR-3 | Material-supply issues | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | PR
PR-4 | Change in project delivery method | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | PR
PR-5 | Accelerate pre-construction activities to reach NTP sooner | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | PR
PR-6 | Use incentives to accelerate D/B construction | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | PR
PR-7 | Issues with D/B design or submittals | No Impact | 0 | 0.75 | 0 | 0 | 0 | 0 |  | No | 0 | PR
CR-6 | Severe weather event significantly impacts construction | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | CR
CR-8 | Significant accident during construction | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | CR
CR-10 | Fish window in Wandering Creek | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | CR
CR-11 | Non-compliance with permits during construction | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | CR
CR-12 | Extended overheads as a function of project delays | No Impact | 0 | 0 | 0 | 0 | 0 | 0 |  | No | 0 | CR
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
<===BACK
FWD===>
HOME

## 11 - Mit. Project Performance
SHRP2 Risk Management Template
HELP |  |  |  |  | Step 11 - Mitigated Project Performance
Schedule Duration Assumption:
Some risks in a phase will occur concurrently, while others will occur sequentially.
Mitigated Project Cost, Duration, and Disruption Performance
Project Phase |  | Base + Implementation |  |  | Residual Risk |  |  | Total (Base + Implementation + Residual Risk)
| Cost (CY $M) | Duration (months) | Disruption (M-hrs) | Cost (CY $M) | Duration (months) | Disruption (M-hrs) | Cost (CY $M) | Duration (months) | Disruption (M-hrs) | Cost (YOE $M)
Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scoping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prelim Design/Environmental Process | 1.19 | 12 | 0 | 0.13125 | 1.414 | 0 | 1.3213 | 13.414 | 0 | 1.3432
Environmental Permits | 0 | 6 | 0 | 0 | 0.3125 | 0 | 0 | 6.3125 | 0 | 0
ROW/Util/RR | 3.05 | 12 | 0.2 | 2.352 | 0.70312 | 0 | 5.402 | 12.7031 | 0.2 | 5.6712
Final Design | 0.2 | 6 | 0 | 0 | 0.75 | 0 | 0.2 | 6.75 | 0 | 0.2119
Procurement | 0 | 6 | 0 | 0.21172 | 0.28906 | 0 | 0.21172 | 6.2891 | 0 | 0.22063
Construction | 11.85 | 16 | 0.5 | 1.8189 | 0.37656 | -0.020463 | 13.6689 | 16.3766 | 0.47954 | 14.6908
Operations & Maintenance | 0 | 600 | 1.4 | 0 | 0 | 0 | 0 | 600 | 1.4
Replacement | 0 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0.7
Total (through Construction) | 16.29 |  | 0.7 | 4.5138 |  | -0.020463 | 20.8038 |  | 0.67954 | 22.1377
Total (through Replacement) | 16.29 |  | 2.8 | 4.5138 |  | -0.020463 | 20.8038 |  | 2.7795 | 22.1377
Project Schedule Performance (Unmitigated vs. Mitigated)
Project Phase |  |  | Unmitigated Project Schedule Performance (from step 6) | [5 empty] | Mitigated Project Schedule Performance |  |  |  | Mean
| Duration (Months/ Date) | Early Start | Early Finish | Late Start | Late Finish | Float (months) | Duration (Months/ Date) | Early Start | Early Finish | Late Start | Late Finish | Float (months) | Severity YOE($M)
Planning | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | 0.013392
Scoping | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | 0.48713
Design Funding Date | 4014800% |  | 4014800% |  | 4014800% | 0 | 4014800% |  | 4014800% |  | 4014800% | 0 | 0
Prelim Design/Environmental Process | 13.414 | 4014800% | 4055579% | 4014800% | 4055579% | 0 | 13.414 | 4014800% | 4055579% | 4014800% | 4055579% | 0 | 1.1813
Environmental Permits | 6.3125 | 4055579% | 4074769% | 4058049% | 4077239% | 0.8125 | 6.3125 | 4055579% | 4074769% | 4056766% | 4075956% | 0.39062 | 0.073452
ROW/Util/RR Funding Date | 4014800% |  | 4014800% |  | 4095479% | 26.539 | 4014800% |  | 4014800% |  | 4094196% | 26.1172 | 0
ROW/Util/RR | 13.125 | 4055579% | 4095479% | 4055579% | 4095479% | 0 | 12.7031 | 4055579% | 4094196% | 4055579% | 4094196% | 0 | 2.2659
Construction Funding Date | 4014800% |  | 4014800% |  | 4058120% | 14.25 | 4014800% |  | 4014800% |  | 4056837% | 13.8281 | 0
Procurement | 6.2891 | 4055579% | 4077239% | 4058120% | 4077239% | 0 | 6.2891 | 4055579% | 4075956% | 4056837% | 4075956% | 0 | 1.0109
Final Design | 6.75 | 4077239% | 4097759% | 4077239% | 4113277% | 5.1047 | 6.75 | 4075956% | 4096476% | 4075956% | 4110541% | 4.6266 | 0
Construction | 16.8547 | 4080279% | 4131517% | 4080279% | 4131517% | 0 | 16.3766 | 4078996% | 4128781% | 4078996% | 4128781% | 0 | 0.20238
Operations & Maintenance | 600 | 4131517% | 5955517% | 4131517% | 5955517% |  | 600 | 4128781% | 5952781% | 4128781% | 5952781%
Replacement | 0 | 5955517% | 5955517% | 5955517% | 5955517% |  | 0 | 5952781% | 5952781% | 5952781% | 5952781%
Project Start Date | 4014800% | [5 empty] | 4014800% |  |  |  |  | Total | 5.2344
Construction Finish Date | 4131517% | [5 empty] | 4128781%
Project Duration (months) | 38.3937 | [5 empty] | 37.4937
<==BACK
FWD==>
HOME
Update Risk Analysis Summary
Makes sure you click on "Create Registers" on Step 8 before running the Risk Analysis

## 12 - Mit. Risk Ranking Plots
SHRP2 Risk Management Template
HELP | Step 12 - Mitigated Risk Ranking Plots
<===BACK
FWD===>
HOME

## 13 - Summary Report
|  | SHRP2 Risk Management Template | [21 empty] | UNMITIGATED PERFORMANCE RESULTS | [21 empty] | MITIGATED PERFORMANCE RESULTS
HELP |  | Summary Report | [27 empty] | Project Performance | [19 empty] | Project Performance
|  |  |  | PROJECT INFORMATION | [19 empty] | Project Phase |  | Base |  |  | Risk |  |  | Total (Base + Risk) | [13 empty] | Project Phase |  | Base + Implementation |  |  | Residual Risk |  |  |  | Total
|  |  | Information Type | Value | [20 empty] | Cost (CY $M) | Duration (months) | Disruption (M-hrs) | Cost (CY $M) | Duration (months) | Disruption (M-hrs) | Cost (CY $M) | Duration (months) | Disruption (M-hrs) | Cost (YOE $M) | [12 empty] | Cost (CY $M) | Duration (months) | Disruption (M-hrs) | Cost (CY $M) | Duration (months) | Disruption (M-hrs) | Cost (CY $M) | Duration (months) | Disruption (M-hrs) | Cost (YOE $M)
| Note: Click on "Update Report" to ensure that this |  | Agency | Federal Highway Administration |  |  | PROJECT STRUCTURING
| summary is populated with the latest data and charts |  | District Region | QDOT District 1 |  |  |  | Base Cost
|  |  | Project Name | QDOT Example |  |  |  | Total Unesc | Total Esc | Duration | [13 empty] | Planning |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | REPORT SUMMARY | Project Description | QDOT Example R09 Guidebook |  |  | Project Phase | Cost ($M) | Cost ($M) | (months) | [13 empty] | Scoping |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Scoping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Facilitator | Carlos F Figueroa |  |  | Planning |  | 0 | 0 |  |  |  | SUMMARY OF RISK IDENTIFICATION | [9 empty] | Prelim Design/Environmental Process | 1.19 | 12 | 0 | 0.13125 | 1.414 | 0 | 1.3213 | 13.414 | 0 | 1.3432 | [11 empty] | Prelim Design/Environmental Process | 1.19 | 12 | 0 | 0.13125 | 1.414 | 0 | 1.3213 | 13.414 | 0 | 1.3432
|  |  | Project Manager | Luis Millan |  |  | Scoping |  | 0 | 0
|  |  | Date | 4224700% |  |  | Prelim Design/Environmental Process | 1.19 | 1.2089 | 12 |  |  |  | Project Phase | Number of Risks Identified in Each Phase
|  |  | Version | 2 |  |  | Environmental Permits |  | 0.00062256 | 6 | [13 empty] | Environmental Permits |  | 6 | 0 | 0 | 0.3125 | 0 | 0 | 6.3125 | 0 | 0 | [11 empty] | Environmental Permits | 0 | 6 | 0 | 0 | 0.3125 | 0 | 0 | 6.3125 | 0 | 0
[7 empty] | ROW/Util/RR | 3 | 3.1371 | 12 |  |  |  | Planning | 4 | [8 empty] | ROW/Util/RR | 3 | 12 | 0.2 | 2.625 | 1.125 | 0 | 5.625 | 13.125 | 0.2 | 5.9084 | [11 empty] | ROW/Util/RR | 3.05 | 12 | 0.2 | 2.352 | 0.70312 | 0 | 5.402 | 12.7031 | 0.2 | 5.6712
[7 empty] | Final Design |  | 0.00062256 | 6 |  |  |  | Scoping | 7 | [8 empty] | Final Design |  | 6 | 0 | 0 | 0.75 | 0 | 0 | 6.75 | 0 | 0 | [11 empty] | Final Design | 0.2 | 6 | 0 | 0 | 0.75 | 0 | 0.2 | 6.75 | 0 | 0.2119
|  |  |  | PROJECT STRUCTURING |  |  | Procurement |  | 0.00063181 | 6 |  |  |  | Design Funding Date | 0 | [8 empty] | Procurement |  | 6 | 0 | 0.2539 | 0.28906 | 0 | 0.2539 | 6.2891 | 0 | 0.26473 | [11 empty] | Procurement | 0 | 6 | 0 | 0.21172 | 0.28906 | 0 | 0.21172 | 6.2891 | 0 | 0.22063
|  |  |  | Summary |  | Units | Construction | 11.85 | 12.6677 | 16 |  |  |  | Prelim Design/Environmental Process | 16 | [8 empty] | Construction | 11.85 | 16 | 0.5 | 2.4604 | 0.85469 | 0.0025 | 14.3104 | 16.8547 | 0.5025 | 15.4052 | [11 empty] | Construction | 11.85 | 16 | 0.5 | 1.8189 | 0.37656 | -0.020463 | 13.6689 | 16.3766 | 0.47954 | 14.6908
|  |  |  | Project Delivery Method | Design-Build |  | Operations & Maintenance | 0 | 0 | 600 |  |  |  | Environmental Permits | 2 | [8 empty] | Operations & Maintenance | 0 | 600 | 1.4 | 0 | 0 | 0 | 0 | 600 | 1.4 | [12 empty] | Op. & Maint. | 0 | 600 | 1.4 | 0 | 0 | 0 | 0 | 600 | 1.4
[5 empty] | Schedule |  | Replacement | 0 | 0 | 0 |  |  |  | ROW/Util/RR Funding Date | 0 | [8 empty] | Replacement | 0 | 0 | 0.7 | 0 |  | 0 | 0 | 0 | 0.7 | [12 empty] | Replacement | 0 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0.7
|  |  |  | Selected Perfomance Measures | Cost | [8 empty] | ROW/Util/RR | 10 | [8 empty] | Total | 16.04 |  | 2.8 | 5.4705 |  | 0.0025 | 21.5105 |  | 2.8025 | 22.9216 | [11 empty] | Total (through Construction) | 16.29 |  | 0.7 | 4.5138 |  | -0.020463 | 20.8038 |  | 0.67954 | 22.1377
[5 empty] | Disruption | [8 empty] | Construction Funding Date | 0
|  |  |  | Project Start Date | 4014800% |  |  |  | Base Schedule |  |  |  |  | Procurement | 8 | [14 empty] | Project Schedule | [20 empty] | Project Schedule
|  |  |  | Target Date for Start of Operations | 4121200% |  | Project Phase | Months/Date | Early Start | Early Finish | Late Start | Late Finish | Float | Final Design | 0 | [8 empty] | Project Phase |  |  | Base Project Schedule Performance | [5 empty] | Unmitigated Project Schedule Performance | [12 empty] | Project Phase |  |  | Unmitigated Project Schedule Performance | [5 empty] | Mitigated Project Schedule Performance
|  |  |  | Preconstruction Inflation Rate | 3 | (%) | Planning | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | Construction | 12 | [9 empty] | Duration (mo./date) | Early Start | Early Finish | Late Start | Late Finish | Float (mo.) | Duration (mo./date) | Early Start | Early Finish | Late Start | Late Finish | Float (mo.) | Mean Severity | [9 empty] | Duration (mo./date) | Early Start | Early Finish | Late Start | Late Finish | Float (mo.) | Duration (mo./date) | Early Start | Early Finish | Late Start | Late Finish | Float (mo.) | Mean Severity
|  |  |  | ROW/Utility/RR Inflation Rate | 3 | (%) | Scoping | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | Operations & Maintenance | 0 | [43 empty] | YOE ($M)
|  |  |  | Construction Inflation Rate | 3 | (%) | Design Funding Date | 4014800% |  | 4014800% |  | 4014800% | 0 | Replacement | 0 | [8 empty] | Planning | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | 0.013392 | [8 empty] | Planning | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | 0.013392
|  |  |  | Preconstruction Overhead Rate | 0.1 | ($ M/month) | Prelim Design/Environmental Process | 12 | 4014800% | 4051280% | 4014800% | 4051280% | 0 | Total | 59 | [8 empty] | Scoping | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | 0.7959 | [8 empty] | Scoping | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | 0 | 4014800% | 4014800% | 4014800% | 4014800% | 0 | 0.48713
|  |  |  | Construction Overhead Rate | 0.225 | ($ M/month) | Environmental Permits | 6 | 4051280% | 4069520% | 4051280% | 4069520% | 0 | [10 empty] | Design Funding Date | 4014800% |  | 4014800% |  | 4014800% | 0 | 4014800% |  | 4014800% |  | 4014800% | 0 | 0 | [8 empty] | Design Funding Date | 4014800% |  | 4014800% |  | 4014800% | 0 | 4014800% |  | 4014800% |  | 4014800% | 0 | 0
|  |  |  | Disruption Value | 10 | ($/day) | ROW/Util/RR Funding Date | 4014800% |  | 4014800% |  | 4087760% | 24 | [10 empty] | Prelim Design/Environmental Process | 12 | 4014800% | 4051280% | 4014800% | 4051280% | 0 | 13.414 | 4014800% | 4055579% | 4014800% | 4055579% | 0 | 1.3677 | [8 empty] | Prelim Design/Environmental Process | 13.414 | 4014800% | 4055579% | 4014800% | 4055579% | 0 | 13.414 | 4014800% | 4055579% | 4014800% | 4055579% | 0 | 1.1813
|  |  |  | Schedule Value | 0.1 | ($ M/month) | ROW/Util/RR | 12 | 4051280% | 4087760% | 4051280% | 4087760% | 0 | [10 empty] | Environmental Permits | 6 | 4051280% | 4069520% | 4051280% | 4069520% | 0 | 6.3125 | 4055579% | 4074769% | 4058049% | 4077239% | 0.8125 | 0.073452 | [21 empty] | 0.073452
|  |  |  | Facility Performance Period | 50 | (years) | Construction Funding Date | 4014800% |  | 4014800% |  | 4051280% | 12 | [10 empty] | ROW/Util/RR Funding Date | 4014800% |  | 4014800% |  | 4087760% | 24 | 4014800% |  | 4014800% |  | 4095479% | 26.539 | 0 | [21 empty] | 0
|  |  |  | Discount Rate | 5 | (%) | Procurement | 6 | 4051280% | 4069520% | 4051280% | 4069520% | 0 | [10 empty] | ROW/Util/RR | 12 | 4051280% | 4087760% | 4051280% | 4087760% | 0 | 13.125 | 4055579% | 4095479% | 4055579% | 4095479% | 0 | 2.4783 | [8 empty] | Environmental Permits | 6.3125 | 4055579% | 4074769% | 4058049% | 4077239% | 0.8125 | 6.3125 | 4055579% | 4074769% | 4056766% | 4075956% | 0.39062 | 2.2659
|  |  |  | Agency/User Discount Factor | 1 |  | Final Design | 6 | 4069520% | 4087760% | 4069520% | 4102960% | 5 | [10 empty] | Construction Funding Date | 4014800% |  | 4014800% |  | 4051280% | 12 | 4014800% |  | 4014800% |  | 4058120% | 14.25 | 0 | [8 empty] | ROW/Util/RR Funding Date | 4014800% |  | 4014800% |  | 4095479% | 26.539 | 4014800% |  | 4014800% |  | 4094196% | 26.1172 | 0
|  |  |  | Total Unescalated Cost |  | ($M) | Construction | 16 | 4072560% | 4121200% | 4072560% | 4121200% | 0 | [10 empty] | Procurement | 6 | 4051280% | 4069520% | 4051280% | 4069520% | 0 | 6.2891 | 4055579% | 4077239% | 4058120% | 4077239% | 0 | 1.0109 | [8 empty] | ROW/Util/RR | 13.125 | 4055579% | 4095479% | 4055579% | 4095479% | 0 | 12.7031 | 4055579% | 4094196% | 4055579% | 4094196% | 0 | 1.0109
|  |  |  | Total Escalated Cost | 17 | ($M) | Operations & Maintenance | 600 | 4121200% | 5945200% | 4121200% | 5945200% | [11 empty] | Final Design | 600% | 4069520% | 4087760% | 4069520% | 4102960% | 5 | 675% | 4077239% | 4097759% | 4077239% | 4113277% | 5.1047 | 0 | [8 empty] | Construction Funding Date | 4014800% |  | 4014800% |  | 4058120% | 14.25 | 4014800% |  | 4014800% |  | 4056837% | 13.8281 | 0
|  |  |  | Base Construction Completion Date | 4121200% |  | Replacement | 0 | 5945200% | 5945200% | 5945200% | 5945200% | [11 empty] | Construction | 16 | 4072560% | 4121200% | 4072560% | 4121200% | 0 | 16.8547 | 4080279% | 4131517% | 4080279% | 4131517% | 0 | 0.90955 | [8 empty] | Procurement | 6.2891 | 4055579% | 4077239% | 4058120% | 4077239% | 0 | 6.2891 | 4055579% | 4075956% | 4056837% | 4075956% | 0 | 0.20238
|  |  |  | Months to Construction Completion | 35 | [18 empty] | Operations & Maintenance | 600 | 4121200% | 5945200% |  |  |  | 600 | [14 empty] | Final Design | 6.75 | 4077239% | 4097759% | 4077239% | 4113277% | 5.1047 | 6.75 | 4075956% | 4096476% | 4075956% | 4110541% | 4.6266
|  |  |  | Dusruption Cost | 28 | ($M) | [17 empty] | Replacement | 0 | 5945200% |  |  |  |  | 0 | [14 empty] | Construction | 16.8547 | 4080279% | 4131517% | 4080279% | 4131517% | 0 | 16.3766 | 4078996% | 4128781% | 4078996% | 4128781% | 0
[24 empty] | Project Start Date | 4014800% | [5 empty] | 4014800% | [5 empty] | 6.6491 | [8 empty] | Operations & Maintenance | 600 | 4131517% | 5955517% |  |  |  | 600 | [5 empty] | 5.2344
[24 empty] | Construction Finish Date | 4121200% | [5 empty] | 4131517% | [14 empty] | Replacement | 0 | 5955517% |  |  |  |  | 0
[24 empty] | Project Duration (months) | 35 | [5 empty] | 38.3937 | [14 empty] | Project Start Date | 4014800% | [5 empty] | 4014800%
[46 empty] | Construction Finish Date | 4131517% | [5 empty] | 4128781%
[8 empty] | Base | Disruption | [6 empty] | UNMITIGATED RISK REGISTER | [29 empty] | Project Duration (months) | 38.3937 | [5 empty] | 37.4937
[7 empty] | Project Phase |  | Disruption | [6 empty] | Risk Label | Risk Description |  |  | Risk Type | Mean Severity (YOE $M) | Percent of Total Severity | Mean Severity Ranking
[8 empty] | M Veh-Hours/Day | No. of Days | M-Hrs | Cost ($M)
[7 empty] | Planning |  |  | 0 | 0
[7 empty] | Scoping |  |  | 0 | 0
[7 empty] | Prelim Design/Environmental Process |  |  | 0 | 0 |  |  |  |  | SC-6 | Provide new lighting throughout project. |  |  | Threat | 0.61753 | 8.321% | 1
[7 empty] | Environmental Permits |  |  | 0 | 0 |  |  |  |  | PR-1 | Uncertainty in construction-cost inflation rate |  |  | Threat | 0.61716 | 8.316% | 2
[7 empty] | ROW/Util/RR | 0.02 | 10 | 0.2 | 2 |  |  |  |  | RR-1 | Uncertainty in ROW inflation rate |  |  | Threat | 0.60365 | 8.134% | 3
[7 empty] | Procurement |  |  | 0 | 0 |  |  |  |  | RR-3 |  |  |  | Threat | 0.60365 | 8.134% | 4
[7 empty] | Final Design |  |  | 0 | 0 |  |  |  |  | RR-8 | QDOT helps City pay for water and sewer-line relocation |  |  | Threat | 0.60365 | 8.134% | 5
[7 empty] | Construction | 0.05 | 10 | 0.5 | 5 |  |  |  |  | RR-2 | Accelerating pace of development in interchange area |  |  | Threat | 0.51205 | 6.9% | 6
[7 empty] | Operations & Maintenance |  |  | 1.4 | 14 |  |  |  |  | CR-2 | Additional Maintenance of Traffic required |  |  | Threat | 0.50631 | 6.822% | 7
[7 empty] | Replacement |  |  | 0.7 | 7 |  |  |  |  | CR-4 | Unable to construct interchange embankments as rapidly as assumed |  |  | Threat | 0.39151 | 5.275% | 8
[7 empty] | Total Disruption through OMR |  |  | 2.8 | 28 |  |  |  |  | PD-13 | Change in environmental documentation. |  |  | Threat | 0.37949 | 5.113% | 9
[16 empty] | PR-2 | Uncertain Design/Build contracting market conditions at time of bid |  |  | Threat | 0.37535 | 5.058% | 10
[16 empty] | PD-11 | Cannot use City sewer system for project runoff (or City charges for use). |  |  | Threat | 0.37493 | 5.052% | 11
[16 empty] | CR-3 | Problems with planned accelerated bridge construction (ABC) technique |  |  | Threat | 0.33372 | 4.497% | 12
[16 empty] | PD-12 | Structures impacted by Main Street realignment are eligible for Historic Register. |  |  | Threat | 0.21316 | 2.872% | 13
[16 empty] | PD-14 | Delays completing environmental documentation. |  |  | Threat | 0.18441 | 2.485% | 14
[16 empty] | PD-4 | Ground improvement required in interchange area. |  |  | Threat | 0.16933 | 2.282% | 15
[16 empty] | SC-5 | Replace culvert over Wandering Creek. |  |  | Threat | 0.11236 | 1.514% | 16
[16 empty] | PD-16 | Additional wetland mitigation required for planned alignment. |  |  | Threat | 0.11221 | 1.512% | 17
[16 empty] | RR-7 | Telecom utility wants a cost-sharing agreement |  |  | Threat | 0.10975 | 1.479% | 18
[16 empty] | PD-5 | Shoulders required on US-555. |  |  | Threat | 0.09805 | 1.321% | 19
[16 empty] | PD-6 | Shoulders required on SH-111. |  |  | Threat | 0.09805 | 1.321% | 20
[16 empty] | CR-5 | Difficult foundation installation |  |  | Threat | 0.075803 | 1.021% | 21
[16 empty] | EP-2 | Delay obtaining the 404 permit |  |  | Threat | 0.073452 | 0.9897% | 22
[16 empty] | SC-3 | Additional local improvements required. |  |  | Threat | 0.066004 | 0.8894% | 23
[16 empty] | RR-6 | Other delays to ROW planning |  |  | Threat | 0.045513 | 0.6133% | 24
[16 empty] | PD-1 | Shift alignment of US 555 at east end of project |  |  | Threat | 0.042611 | 0.5742% | 25
[16 empty] | PD-15 | Encounter unanticipated contamination in interchange area. |  |  | Threat | 0.03206 | 0.432% | 26
[16 empty] | CR-9 | Limited construction staging area in vicinity of interchange |  |  | Threat | 0.03206 | 0.432% | 27
[16 empty] | PR-8 | Other problems with D/B contract procurement |  |  | Threat | 0.018358 | 0.2474% | 28
[16 empty] | PL-2 | Opposition to removing access to US-555 fro 12th St. |  |  | Threat | 0.013392 | 0.1804% | 29
[16 empty] | CR-7 | Colder-than-usual winter |  |  | Threat | 0.0058071 | 0.07825% | 30
[16 empty] | CR-1 | D/B construction phasing significantly different than assumed |  |  | Opportunity | -0.43567 | 56.41% | 1
[16 empty] | PD-8 | Change in pavement section and/or type. |  |  | Opportunity | -0.33663 | 43.59% | 2
[16 empty] | PL-3 | Opposition to "splitting" alignment of SH-111 in the interchange area. |  |  | No Impact | 0 | 0%
[16 empty] | PL-4 | Other stakeholder issues not captured separately. |  |  | No Impact | 0 | 0%
[16 empty] | PL-5 | Project funding delayed or reduced. |  |  | No Impact | 0 | 0%
[16 empty] | SC-1 | Change in East-West project limits. |  |  | No Impact | 0 | 0%
[16 empty] | SC-2 | Change in North-South project limits. |  |  | No Impact | 0 | 0%
[16 empty] | SC-4 | Increased aestethetics for US-555/SH-111 interchange. |  |  | No Impact | 0 | 0%
[16 empty] | SC-7 | ITS added to this project. |  |  | No Impact | 0 | 0%
[16 empty] | PD-2 | Split alignment of SH-111 at US-555 interchange. |  |  | No Impact | 0 | 0%
[16 empty] | PD-3 | Change in configuration of SH 111 / US 555 interchange. |  |  | No Impact | 0 | 0%
[16 empty] | PD-7 | Additional cost for signalized intersections. |  |  | No Impact | 0 | 0%
[16 empty] | PD-9 | Rehabilitate instead of reconstruct existing roadway (e.g., overlay instead). |  |  | No Impact | 0 | 0%
[16 empty] | PD-10 | Change in stormwater design standards. |  |  | No Impact | 0 | 0%
[16 empty] | EP-1 | Challenge to environmental determination or permits |  |  | No Impact | 0 | 0%
[16 empty] | RR-4 | Additional relocation or demolition required |  |  | No Impact | 0 | 0%
[16 empty] | RR-5 | Additional ROW required for planned project |  |  | No Impact | 0 | 0%
[16 empty] | RR-9 | Other utility relocations not completed on time |  |  | No Impact | 0 | 0%
[16 empty] | RR-10 | Damage existing utility or encounter unanticipated utility during construction |  |  | No Impact | 0 | 0%
[16 empty] | PR-3 | Material-supply issues |  |  | No Impact | 0 | 0%
[16 empty] | PR-4 | Change in project delivery method |  |  | No Impact | 0 | 0%
[16 empty] | PR-5 | Accelerate pre-construction activities to reach NTP sooner |  |  | No Impact | 0 | 0%
[16 empty] | PR-6 | Use incentives to accelerate D/B construction |  |  | No Impact | 0 | 0%
[16 empty] | PR-7 | Issues with D/B design or submittals |  |  | No Impact | 0 | 0%
[16 empty] | CR-6 | Severe weather event significantly impacts construction |  |  | No Impact | 0 | 0%
[16 empty] | CR-8 | Significant accident during construction |  |  | No Impact | 0 | 0%
[16 empty] | CR-10 | Fish window in Wandering Creek |  |  | No Impact | 0 | 0%
[16 empty] | CR-11 | Non-compliance with permits during construction |  |  | No Impact | 0 | 0%
[16 empty] | CR-12 | Extended overheads as a function of project delays |  |  | No Impact | 0 | 0%
MITIGATED RISK REGISTER
[16 empty] | Risk Label | Risk Description | Risk Type | Mean Severity Value (YOE $M) | Mitigated Mean Severity Value (YOE $M) | Percent Change in Mean Severity Value | Percent of Total Mitigated Severity Value | Mean Severity Ranking
[16 empty] | RR-8 | QDOT helps City pay for water and sewer-line relocation | Threat | 0.94937 | 0.94937 | 0% | 15.8% | 1
[16 empty] | PR-1 | Uncertainty in construction-cost inflation rate | Threat | 0.61716 | 0.61716 | 0% | 10.27% | 2
[16 empty] | RR-1 | Uncertainty in ROW inflation rate | Threat | 0.60365 | 0.60365 | 0% | 10.05% | 3
[16 empty] | PD-13 | Change in environmental documentation. | Threat | 0.37949 | 0.37949 | 0% | 6.315% | 4
[16 empty] | PR-2 | Uncertain Design/Build contracting market conditions at time of bid | Threat | 0.37535 | 0.37535 | 0% | 6.246% | 5
[16 empty] | SC-6 | Provide new lighting throughout project. | Threat | 0.30876 | 0.30876 | 0% | 5.138% | 6
[16 empty] | RR-3 | Unwilling sellers | Threat | 0.30182 | 0.30182 | 0% | 5.023% | 7
[16 empty] | RR-2 | Accelerating pace of development in interchange area | Threat | 0.25583 | 0.25583 | 0% | 4.257% | 8
[16 empty] | PD-12 | Structures impacted by Main Street realignment are eligible for Historic Register. | Threat | 0.21316 | 0.21316 | 0% | 3.547% | 9
[16 empty] | CR-4 | Unable to construct interchange embankments as rapidly as assumed | Threat | 0.19762 | 0.19762 | 0% | 3.289% | 10
[16 empty] | PD-11 | Cannot use City sewer system for project runoff (or City charges for use). | Threat | 0.18742 | 0.18742 | 0% | 3.119% | 11
[16 empty] | PD-14 | Delays completing environmental documentation. | Threat | 0.18441 | 0.18441 | 0% | 3.069% | 12
[16 empty] | PD-4 | Ground improvement required in interchange area. | Threat | 0.16975 | 0.16975 | 0% | 2.825% | 13
[16 empty] | CR-3 | Problems with planned accelerated bridge construction (ABC) technique | Threat | 0.16772 | 0.16772 | 0% | 2.791% | 14
[16 empty] | CR-2 | Additional Maintenance of Traffic required | Threat | 0.1612 | 0.1612 | 0% | 2.683% | 15
[16 empty] | SC-5 | Replace culvert over Wandering Creek. | Threat | 0.11236 | 0.11236 | 0% | 1.87% | 16
[16 empty] | PD-16 | Additional wetland mitigation required for planned alignment. | Threat | 0.11221 | 0.11221 | 0% | 1.867% | 17
[16 empty] | RR-7 | Telecom utility wants a cost-sharing agreement | Threat | 0.10975 | 0.10975 | 0% | 1.826% | 18
[16 empty] | PD-5 | Shoulders required on US-555. | Threat | 0.098384 | 0.098384 | 0% | 1.637% | 19
[16 empty] | PD-6 | Shoulders required on SH-111. | Threat | 0.098384 | 0.098384 | 0% | 1.637% | 20
[16 empty] | CR-5 | Difficult foundation installation | Threat | 0.07622 | 0.07622 | 0% | 1.268% | 21
[16 empty] | EP-2 | Delay obtaining the 404 permit | Threat | 0.073452 | 0.073452 | 0% | 1.222% | 22
[16 empty] | SC-3 | Additional local improvements required. | Threat | 0.066004 | 0.066004 | 0% | 1.098% | 23
[16 empty] | RR-6 | Other delays to ROW planning | Threat | 0.045513 | 0.045513 | 0% | 0.7574% | 24
[16 empty] | PD-1 | Shift alignment of US 555 at east end of project | Threat | 0.042611 | 0.042611 | 0% | 0.7091% | 25
[16 empty] | PD-15 | Encounter unanticipated contamination in interchange area. | Threat | 0.03206 | 0.03206 | 0% | 0.5335% | 26
[16 empty] | CR-9 | Limited construction staging area in vicinity of interchange | Threat | 0.03206 | 0.03206 | 0% | 0.5335% | 27
[16 empty] | PR-8 | Other problems with D/B contract procurement | Threat | 0.018358 | 0.018358 | 0% | 0.3055% | 28
[16 empty] | PL-2 | Opposition to removing access to US-555 fro 12th St. | Threat | 0.013392 | 0.013392 | 0% | 0.2228% | 29
[16 empty] | CR-7 | Colder-than-usual winter | Threat | 0.0058906 | 0.0058906 | 0% | 0.09802% | 30
[16 empty] | CR-1 | D/B construction phasing significantly different than assumed | Opportunity | -0.43833 | -0.43833 | 0% | 56.56% | 1
[16 empty] | PD-8 | Change in pavement section and/or type. | Opportunity | -0.33663 | -0.33663 | 0% | 43.44% | 2
[16 empty] | PL-3 | Opposition to "splitting" alignment of SH-111 in the interchange area. | No Impact | 0 | 0 | 0% | 0%
[16 empty] | PL-4 | Other stakeholder issues not captured separately. | No Impact | 0 | 0 | 0% | 0%
[16 empty] | PL-5 | Project funding delayed or reduced. | No Impact | 0 | 0 | 0% | 0%
[16 empty] | SC-1 | Change in East-West project limits. | No Impact | 0 | 0 | 0% | 0%
[16 empty] | SC-2 | Change in North-South project limits. | No Impact | 0 | 0 | 0% | 0%
[16 empty] | SC-4 | Increased aestethetics for US-555/SH-111 interchange. | No Impact | 0 | 0 | 0% | 0%
[16 empty] | SC-7 | ITS added to this project. | No Impact | 0 | 0 | 0% | 0%
[16 empty] | PD-2 | Split alignment of SH-111 at US-555 interchange. | No Impact | 0 | 0 | 0% | 0%
[16 empty] | PD-3 | Change in configuration of SH 111 / US 555 interchange. | No Impact | 0 | 0 | 0% | 0%
[16 empty] | PD-7 | Additional cost for signalized intersections. | No Impact | 0 | 0 | 0% | 0%
[16 empty] | PD-9 | Rehabilitate instead of reconstruct existing roadway (e.g., overlay instead). | No Impact | 0 | 0 | 0% | 0%
[16 empty] | PD-10 | Change in stormwater design standards. | No Impact | 0 | 0 | 0% | 0%
[16 empty] | EP-1 | Challenge to environmental determination or permits | No Impact | 0 | 0 | 0% | 0%
[16 empty] | RR-4 | Additional relocation or demolition required | No Impact | 0 | 0 | 0% | 0%
[16 empty] | RR-5 | Additional ROW required for planned project | No Impact | 0 | 0 | 0% | 0%
[16 empty] | RR-9 | Other utility relocations not completed on time | No Impact | 0 | 0 | 0% | 0%
[16 empty] | RR-10 | Damage existing utility or encounter unanticipated utility during construction | No Impact | 0 | 0 | 0% | 0%
[16 empty] | PR-3 | Material-supply issues | No Impact | 0 | 0 | 0% | 0%
[16 empty] | PR-4 | Change in project delivery method | No Impact | 0 | 0 | 0% | 0%
[16 empty] | PR-5 | Accelerate pre-construction activities to reach NTP sooner | No Impact | 0 | 0 | 0% | 0%
[16 empty] | PR-6 | Use incentives to accelerate D/B construction | No Impact | 0 | 0 | 0% | 0%
[16 empty] | PR-7 | Issues with D/B design or submittals | No Impact | 0 | 0 | 0% | 0%
[16 empty] | CR-6 | Severe weather event significantly impacts construction | No Impact | 0 | 0 | 0% | 0%
[16 empty] | CR-8 | Significant accident during construction | No Impact | 0 | 0 | 0% | 0%
[16 empty] | CR-10 | Fish window in Wandering Creek | No Impact | 0 | 0 | 0% | 0%
[16 empty] | CR-11 | Non-compliance with permits during construction | No Impact | 0 | 0 | 0% | 0%
[16 empty] | CR-12 | Extended overheads as a function of project delays | No Impact | 0 | 0 | 0% | 0%
STRATEGY REGISTER
[38 empty] | Risk Label | Risk Description | Selected Strategy | Mitigated Severity | Benefit/ Cost Analysis | Responsibility | Schedule /Milestone | Comments
[38 empty] | SC-6 | Provide new lighting throughout project. | Negotiate cost sharing agreement with the city | 50 | No Cost | Project Director | Midway thru prelim design
[38 empty] | RR-3 | Unwilling sellers | Make reasonable early offer | 50 | 5.775 | Project Engineer | Midway thru ROW/Util/RR
[38 empty] | CR-2 | Additional Maintenance of Traffic required | Reduce traffic demand during closures | 68.1841 | 6.5616 | Project Engineer | Midway thru final design
[38 empty] | RR-2 | Accelerating pace of development in interchange area | Coordinate with City - stop issuing permits for new developments | 50.0381 | No Cost | Project Engineer | Midway thru prelim design
[38 empty] | PD-11 | Cannot use City sewer system for project runoff (or City charges for use). | Same action as RR8 (affects RR8 and PD11) | 50.0109 | No Cost | Project Engineer | Midway thru prelim design
[38 empty] | RR-8 | QDOT helps City pay for water and sewer-line relocation | Decide to help city pay for water and sewer line relocation | -57.2727 | No Cost
[38 empty] | CR-4 | Unable to construct interchange embankments as rapidly as assumed | Conduct additional investigations and analysis to develop at techniques | 50.036 | 1.8794 | Project Engineer | Midway thru final design
[38 empty] | CR-3 | Problems with planned accelerated bridge construction (ABC) technique | Pre-qualify contractors + require development of ABC technique | 50.0187 | 3.1878 | Project Engineer | Midway thru final design
PROJECT NOTES
[60 empty] | Note # | Analysis Step | Note
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
CHARTS
UNMITIGATED RISK RANKING PLOTS - THREATS
UNMITIGATED RISK RANKING PLOTS - OPPORTUNITIES
MITIGATED RISK RANKING PLOTS - THREATS
MITIGATED RISK RANKING PLOTS - OPPORTUNITIES
BACK TO SUMMARY
BACK TO SUMMARY
BACK TO SUMMARY
BACK TO SUMMARY
BACK TO SUMMARY
BACK TO SUMMARY
BACK TO SUMMARY
BACK TO SUMMARY
BACK TO SUMMARY
BACK TO SUMMARY
BACK TO SUMMARY
<==BACK
HOME
PRINT REPORT
BACK TO SUMMARY
UPDATE REPORT
COPY
COPY
COPY
COPY
COPY
COPY
COPY
COPY
COPY
COPY
COPY
COPY
COPY
COPY
COPY
COPY
TABLES
PROJECT INFORMATION
PROJECT STRUCTURING
RISK IDENTIFICATION
MITIGATED PROJECT PERFORMANCE
UNMITIGATED PROJECT PERFORMANCE
MITIGATION STRATEGIES REGISTER
MITIGATED RISK REGISTER
UNMITIGATED RISK REGISTER
PROJECT NOTES
BACK TO SUMMARY
COPY
COPY